## 1. 표지(최초, 정기)
PJT : BOSK TN1 Aging & Convyeyor System
2024. 08. 19
| 결 재 | 작성(담당) |  | 검토 | 승인
|  | 근로자(대표) | 관리감독자 | 안전관리자 | 현장소장 (안전보건관리책임자)
위험성 평가표 결과서

## 2. 위험성평가실시계획(공사개요)(최초, 정기)
2. 위험성 평가 실시 계획(공사개요)
부서명 | PM 3팀 |  |  | 담당자명 | 이창노 |  | 현장명 | BOSK TN
공사개요 | [6 empty] | 위험성평가 추진 일정(계획)
공사금액(VAT포함) |  | 85854300 |  |  |  |  | 평가구분 | 최초 / 정기 / 수시
현장소장/연락처 |  | 이찬희 / 010-6565-1637 |  |  |  |  | 단계 | 추진일정 | 담당 인원
공사기간 |  | 2024-09-23~ 2025-01-15 |  |  |  |  | 1. 사전준비 | 2024-08-19 | 이찬희 수석
현장주소 |  | 2025 BlueOval City Drive STANTON, TENNESSEE, 38069, UNITED STATES
발주처 |  | BOSK |  |  |  |  | 2. 유해위험요인파악 | 2024-08-19 | 이찬희 수석
평균출력인원 |  | 20
주요장비 목록 (대수) |  | CONVEYOR |  |  |  |  | 3. 위험성 추정 | 2024-08-19 | 이찬희 수석
RACK
협력회사 |  | 회사명 | DPM | AMD | 피아물류 | 세진FA | 4. 위험성 결정 | 2024-08-19 | 이찬희 수석
|  | 공종 | CV,MSC,RACK H/W SET-UP
|  | 회사명 | 대양산전 | 한국자동화 | 바이너리 |  | 5. 위험성 감소대책 수립 및 실행 | 2024-08-19 | 이찬희 수석
|  | 공종 | CV, MSC 전장 및 제어
|  | 회사명 | 뉴엔텍 | CS프론트라인 | 아이엘스엘 | 그래비티시스템 | 검토자 의견 (적정/수정/보완/재실시 및 사유 등)
|  | 공종 | BCR,WMS,CCTV 제어
위험성 평가 대상 공정(작업) 목록 |  | - CV,MSC,RACK,DECK,LIFT H/W SET-UP - CV, MSC 전장 및 제어 -. CV,MSC 시운전
94439400

## 3. 위험성평가 조직도(최초, 정기)
3. 위험성 평가 조직 구성
대표이사
김영민
안전보건관리책임자
이창노
안전관리자 |  |  |  | 보건관리자
윤은지
<H/W SET-UP> |  | <전장/제어/시운전> |  | <S/W정보>
관리감독자 | 이찬희 | 관리감독자 | 정광욱 | 관리감독자 | 이승준
협력사명 | 세진FA | 협력사명 | 대양산전 | 협력사명 | 뉴엔텍
소장 | 김진욱 | 소장 | 강민수 | 소장 | 유인호
협력사명 | DPM | 협력사명 | 한국자동화 | 협력사명 | CS프론트라인
소장 | 박경원 | 소장 | 서영한 | 소장 | 금무경
협력사명 | ADM | 협력사명 | 바이너리 | 협력사명 | 아이에스엘
소장 | 강원모 | 소장 | 박태진 | 소장 | 심재현
협력사명 | 피아물류 |  |  | 협력사명 | 그래비티시스템
소장 | 김관용 |  |  | 소장 | 차명환
협력사명 | 휴먼
소장 | 박승진

## 4. 전체공사일정
BOSK TN1 Aging & Convyeyor System
[25 empty] | #NAME? | W1 |  |  |  | W5 |  |  |  | W9 |  |  |  | W13 |  |  |  | W17 |  |  |  | W21 |  |  |  | W25 |  |  |  | W29 |  |  |  | W33 |  |  |  | W37 |  |  |  | W41 |  |  |  | W45 |  |  |  | W49 |  |  |  | W53 |  |  |  | W57 |  |  |  | W61 |  |  |  | W65 |  |  |  | W69 |  |  |  | W73 |  |  |  | W77 |  |  |  | W81 |  |  |  | W85
reserved | task_group | wbs_level | WBS | 작업* |  |  |  |  | 비고 | 시작일* | 완료일* | Calendar | 총 작업량 | 계획 작업량 | 총 기간 | 계획 기간 | 실제 시작일 | 실제 완료일 | 실제 총작업량 | 실제 총기간 | 가중치 | 담당 | 산출물 | 계획 | 실적* | 2023 W5 |  |  |  | 02/26 W9 |  |  |  | 03/26 W13 |  |  |  | 04/23 W17 |  |  |  | 05/21 W21 |  |  |  | 06/18 W25 |  |  |  | 07/16 W29 |  |  |  | 08/13 W33 |  |  |  | 09/10 W37 |  |  |  | 10/08 W41 |  |  |  | 11/05 W45 |  |  |  | 12/03 W49 |  |  |  | 12/31 W53 |  |  |  | 2024 W5 |  |  |  | 02/25 W9 |  |  |  | 03/24 W13 |  |  |  | 04/21 W17 |  |  |  | 05/19 W21 |  |  |  | 06/16 W25 |  |  |  | 07/14 W29 |  |  |  | 08/11 W33 |  |  |  | 09/08 W37
 | time axis 2023-01-29 to 2024-09-29
| G | 1 | 1 | 설계 | [5 empty] | 2023-02-01 | 2023-04-30 |  | 529 | 274 | 89 | 43 |  |  | 0 | 0 |  |  |  | 51.8% | 4.149% | 2023-02-05: 4.15%; 2023-04-30: 설계 2/1-4/30
| G | 2 | 1.1 |  | BOSK TN |  |  |  |  | 2023-02-01 | 2023-04-30 |  | 529 | 274 | 89 | 43 |  |  | 0 | 0 |  |  |  | 51.8% | 4.149% | 2023-02-05: 4.15%; 2023-04-30: BOSK TN 2/1-4/30
|  | 3 | 1.1.1 |  |  | Layout |  |  |  | 2023-02-01 | 2023-02-28 |  | 28 | 28 | 28 | 28 |  |  |  | 0 | 1 |  |  | 100% | 11% | 2023-01-29: 11.00%; 2023-02-26: Layout 2/1-2/28
| G | 3 | 1.1.2 |  |  | Rack |  |  |  | 2023-02-01 | 2023-04-15 |  | 127 | 86 | 74 | 43 |  |  | 0 | 0 |  |  |  | 67.72% | 5.283% | 2023-02-05: 5.28%; 2023-04-16: Rack 2/1-4/15
|  | 4 | 1.1.2.1 |  |  |  | DR |  |  | 2023-04-01 | 2023-04-10 |  | 10 | 0 | 10 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-03-26: 0.00% DR 4/1-4/10
| G | 4 | 1.1.2.2 |  |  |  | Aging 창고 |  |  | 2023-02-01 | 2023-04-15 |  | 117 | 86 | 74 | 43 |  |  | 0 | 0 |  |  |  | 73.5% | 5.735% | 2023-02-05: 5.74%; 2023-04-16: Aging 창고 2/1-4/15
|  | 5 | 1.1.2.2.1 |  |  |  |  | Layout 확정 및 기초설계 |  | 2023-02-01 | 2023-03-15 |  | 43 | 43 | 43 | 43 |  |  |  | 0 | 1 |  |  | 100% | 7% | 2023-01-29: 7.00%; 2023-03-12: Layout 확정 및 기초설계 2/1-3/15
|  | 5 | 1.1.2.2.2 |  |  |  |  | 상세설계 |  | 2023-02-01 | 2023-04-15 |  | 74 | 43 | 74 | 43 |  |  |  | 0 | 1 |  |  | 58.11% | 5% | 2023-02-05: 5.00%; 2023-04-16: 상세설계 2/1-4/15
| G | 3 | 1.1.3 |  |  | MSC Crane |  |  |  | 2023-02-01 | 2023-04-30 |  | 359 | 160 | 89 | 43 |  |  | 0 | 0 |  |  |  | 44.57% | 3.387% | 2023-01-29: 3.39%; 2023-04-30: MSC Crane 2/1-4/30
|  | 4 | 1.1.3.1 |  |  |  | 장납기 구매품 발주(모터류) |  |  | 2023-02-15 | 2023-02-28 |  | 14 | 14 | 14 | 14 |  |  |  | 0 | 1 |  |  | 100% | 0% | 2023-02-12: 0.00% 장납기 구매품 발주(모터류) 2/15-2/28
|  | 4 | 1.1.3.2 |  |  |  | DR |  |  | 2023-04-01 | 2023-04-15 |  | 15 | 0 | 15 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-03-26: 0.00% DR 4/1-4/15
| G | 4 | 1.1.3.3 |  |  |  | 상온/고온 Aging, 충방전 |  |  | 2023-02-01 | 2023-04-30 |  | 165 | 73 | 89 | 43 |  |  | 0 | 0 |  |  |  | 44.24% | 3.685% | 2023-01-29: 3.68%; 2023-04-30: 상온/고온 Aging, 충방전 2/1-4/30
|  | 5 | 1.1.3.3.1 |  |  |  |  | Concept (R/Sketch) |  | 2023-02-01 | 2023-02-15 |  | 15 | 15 | 15 | 15 |  |  |  | 0 | 1 |  |  | 100% | 20% | 2023-01-29: 20.00% Concept (R/Sketch) 2/1-2/15
|  | 5 | 1.1.3.3.2 |  |  |  |  | Assy |  | 2023-02-01 | 2023-02-28 |  | 28 | 28 | 28 | 28 |  |  |  | 0 | 1 |  |  | 100% | 11% | 2023-01-29: 11.00%; 2023-02-26: Assy 2/1-2/28
|  | 5 | 1.1.3.3.3 |  |  |  |  | Part - (Main Frame) |  | 2023-03-01 | 2023-04-30 |  | 61 | 15 | 61 | 15 |  |  |  | 0 | 1 |  |  | 24.59% | 0% | 2023-02-26: 0.00%; 2023-04-30: Part - (Main Frame) 3/1-4/30
|  | 5 | 1.1.3.3.4 |  |  |  |  | Part - (Carriage/Fork) |  | 2023-03-01 | 2023-04-30 |  | 61 | 15 | 61 | 15 |  |  |  | 0 | 1 |  |  | 24.59% | 0% | 2023-02-26: 0.00%; 2023-04-30: Part - (Carriage/Fork) 3/1-4/30
| G | 4 | 1.1.3.4 |  |  |  | PPC |  |  | 2023-02-01 | 2023-04-30 |  | 165 | 73 | 89 | 43 |  |  | 0 | 0 |  |  |  | 44.24% | 3.685% | 2023-01-29: 3.68%; 2023-04-30: PPC 2/1-4/30
|  | 5 | 1.1.3.4.1 |  |  |  |  | Concept (R/Sketch) |  | 2023-02-01 | 2023-02-15 |  | 15 | 15 | 15 | 15 |  |  |  | 0 | 1 |  |  | 100% | 20% | 2023-01-29: 20.00% Concept (R/Sketch) 2/1-2/15
|  | 5 | 1.1.3.4.2 |  |  |  |  | Assy |  | 2023-02-01 | 2023-02-28 |  | 28 | 28 | 28 | 28 |  |  |  | 0 | 1 |  |  | 100% | 11% | 2023-01-29: 11.00%; 2023-02-26: Assy 2/1-2/28
|  | 5 | 1.1.3.4.3 |  |  |  |  | Part - (Main Frame) |  | 2023-03-01 | 2023-04-30 |  | 61 | 15 | 61 | 15 |  |  |  | 0 | 1 |  |  | 24.59% | 0% | 2023-02-26: 0.00%; 2023-04-30: Part - (Main Frame) 3/1-4/30
|  | 5 | 1.1.3.4.4 |  |  |  |  | Part - (Carriage/Fork) |  | 2023-03-01 | 2023-04-30 |  | 61 | 15 | 61 | 15 |  |  |  | 0 | 1 |  |  | 24.59% | 0% | 2023-02-26: 0.00%; 2023-04-30: Part - (Carriage/Fork) 3/1-4/30
| G | 3 | 1.1.4 |  |  | Conveyor |  |  |  | 2023-04-01 | 2023-04-15 |  | 15 | 0 | 15 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-03-26: 0.00% Conveyor 4/1-4/15
|  | 4 | 1.1.4.1 |  |  |  | DR |  |  | 2023-04-01 | 2023-04-15 |  | 15 | 0 | 15 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-03-26: 0.00% DR 4/1-4/15
| G | 1 | 2 | 제작 | [5 empty] | 2023-02-15 | 2023-11-30 |  | 24917 | 812 | 289 | 29 |  |  | 0 | 0 |  |  |  | 3.259% | 0% | 2023-02-12: 0.00%; 2023-11-26: 제작 2/15-11/30
| G | 2 | 2.1 |  | BOSK TN |  |  |  |  | 2023-02-15 | 2023-11-30 |  | 24917 | 812 | 289 | 29 |  |  | 0 | 0 |  |  |  | 3.259% | 0% | 2023-02-12: 0.00%; 2023-11-26: BOSK TN 2/15-11/30
| G | 3 | 2.1.1 |  |  | Rack |  |  |  | 2023-04-01 | 2023-09-30 |  | 7682 | 0 | 183 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-03-26: 0.00%; 2023-10-01: Rack 4/1-9/30
| G | 4 | 2.1.1.1 |  |  |  | 상온#1 Aging, FCH (Deck&Accessory) |  |  | 2023-04-01 | 2023-07-30 |  | 637 | 0 | 121 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-03-26: 0.00%; 2023-07-30: 상온#1 Aging, FCH (Deck&Accessory) 4/1-7/30
|  | 5 | 2.1.1.1.1 |  |  |  |  | 단품 및 Post 생산/제작 | 1 | 2023-04-01 | 2023-06-30 | 90 | 455 | 0 | 91 | 0 |  |  |  | 0 | 5 |  |  | 0% | 0% | 2023-03-26: 0.00%; 2023-06-25: 단품 및 Post 생산/제작 4/1-6/30
|  | 5 | 2.1.1.1.2 |  |  |  |  | 1차조립 | 1 | 2023-05-01 | 2023-07-30 | 90 | 182 | 0 | 91 | 0 |  |  |  | 0 | 2 |  |  | 0% | 0% | 2023-04-30: 0.00%; 2023-07-30: 1차조립 5/1-7/30
| G | 4 | 2.1.1.2 |  |  |  | 고온#1 Aging (Deck&Accessory) |  |  | 2023-04-01 | 2023-07-30 |  | 637 | 0 | 121 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-03-26: 0.00%; 2023-07-30: 고온#1 Aging (Deck&Accessory) 4/1-7/30
|  | 5 | 2.1.1.2.1 |  |  |  |  | 단품 및 Post 생산/제작 | 2 | 2023-04-01 | 2023-06-30 | 90 | 455 | 0 | 91 | 0 |  |  |  | 0 | 5 |  |  | 0% | 0% | 2023-03-26: 0.00%; 2023-06-25: 단품 및 Post 생산/제작 4/1-6/30
|  | 5 | 2.1.1.2.2 |  |  |  |  | 1차조립 | 2 | 2023-05-01 | 2023-07-30 | 90 | 182 | 0 | 91 | 0 |  |  |  | 0 | 2 |  |  | 0% | 0% | 2023-04-30: 0.00%; 2023-07-30: 1차조립 5/1-7/30
| G | 4 | 2.1.1.3 |  |  |  | PPC (Deck&Accessory) |  |  | 2023-04-15 | 2023-08-15 |  | 646 | 0 | 123 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-04-09: 0.00%; 2023-08-13: PPC (Deck&Accessory) 4/15-8/15
|  | 5 | 2.1.1.3.1 |  |  |  |  | 단품 및 Post 생산/제작 | 3 | 2023-04-15 | 2023-07-15 | 91 | 460 | 0 | 92 | 0 |  |  |  | 0 | 5 |  |  | 0% | 0% | 2023-04-09: 0.00%; 2023-07-16: 단품 및 Post 생산/제작 4/15-7/15
|  | 5 | 2.1.1.3.2 |  |  |  |  | 1차조립 | 3 | 2023-05-15 | 2023-08-15 | 92 | 186 | 0 | 93 | 0 |  |  |  | 0 | 2 |  |  | 0% | 0% | 2023-05-14: 0.00%; 2023-08-13: 1차조립 5/15-8/15
| G | 4 | 2.1.1.4 |  |  |  | 충방전 (Deck&Accessory) |  |  | 2023-04-15 | 2023-08-15 |  | 646 | 0 | 123 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-04-09: 0.00%; 2023-08-13: 충방전 (Deck&Accessory) 4/15-8/15
|  | 5 | 2.1.1.4.1 |  |  |  |  | 단품 및 Post 생산/제작 | 4 | 2023-04-15 | 2023-07-15 | 91 | 460 | 0 | 92 | 0 |  |  |  | 0 | 5 |  |  | 0% | 0% | 2023-04-09: 0.00%; 2023-07-16: 단품 및 Post 생산/제작 4/15-7/15
|  | 5 | 2.1.1.4.2 |  |  |  |  | 1차조립 | 4 | 2023-05-15 | 2023-08-15 | 92 | 186 | 0 | 93 | 0 |  |  |  | 0 | 2 |  |  | 0% | 0% | 2023-05-14: 0.00%; 2023-08-13: 1차조립 5/15-8/15
| G | 4 | 2.1.1.5 |  |  |  | 고온#2 Aging (Deck&Accessory) |  |  | 2023-04-15 | 2023-08-30 |  | 751 | 0 | 138 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-04-09: 0.00%; 2023-08-27: 고온#2 Aging (Deck&Accessory) 4/15-8/30
|  | 5 | 2.1.1.5.1 |  |  |  |  | 단품 및 Post 생산/제작 | 5 | 2023-04-15 | 2023-07-30 | 106 | 535 | 0 | 107 | 0 |  |  |  | 0 | 5 |  |  | 0% | 0% | 2023-04-09: 0.00%; 2023-07-30: 단품 및 Post 생산/제작 4/15-7/30
|  | 5 | 2.1.1.5.2 |  |  |  |  | 1차조립 | 5 | 2023-05-15 | 2023-08-30 | 107 | 216 | 0 | 108 | 0 |  |  |  | 0 | 2 |  |  | 0% | 0% | 2023-05-14: 0.00%; 2023-08-27: 1차조립 5/15-8/30
| G | 4 | 2.1.1.6 |  |  |  | 상온#2 Aging (Deck&Accessory) |  |  | 2023-04-15 | 2023-08-30 |  | 751 | 0 | 138 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-04-09: 0.00%; 2023-08-27: 상온#2 Aging (Deck&Accessory) 4/15-8/30
|  | 5 | 2.1.1.6.1 |  |  |  |  | 단품 및 Post 생산/제작 | 6 | 2023-04-15 | 2023-07-30 | 106 | 535 | 0 | 107 | 0 |  |  |  | 0 | 5 |  |  | 0% | 0% | 2023-04-09: 0.00%; 2023-07-30: 단품 및 Post 생산/제작 4/15-7/30
|  | 5 | 2.1.1.6.2 |  |  |  |  | 1차조립 | 6 | 2023-05-15 | 2023-08-30 | 107 | 216 | 0 | 108 | 0 |  |  |  | 0 | 2 |  |  | 0% | 0% | 2023-05-14: 0.00%; 2023-08-27: 1차조립 5/15-8/30
| G | 4 | 2.1.1.7 |  |  |  | 공Tray Buffer |  |  | 2023-04-15 | 2023-08-30 |  | 751 | 0 | 138 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-04-09: 0.00%; 2023-08-27: 공Tray Buffer 4/15-8/30
|  | 5 | 2.1.1.7.1 |  |  |  |  | 단품 및 Post 생산/제작 | 6 | 2023-04-15 | 2023-07-30 | 106 | 535 | 0 | 107 | 0 |  |  |  | 0 | 5 |  |  | 0% | 0% | 2023-04-09: 0.00%; 2023-07-30: 단품 및 Post 생산/제작 4/15-7/30
|  | 5 | 2.1.1.7.2 |  |  |  |  | 1차조립 | 6 | 2023-05-15 | 2023-08-30 | 107 | 216 | 0 | 108 | 0 |  |  |  | 0 | 2 |  |  | 0% | 0% | 2023-05-14: 0.00%; 2023-08-27: 1차조립 5/15-8/30
| G | 4 | 2.1.1.8 |  |  |  | RACK 기타 마감자재 |  |  | 2023-08-01 | 2023-09-30 |  | 305 | 0 | 61 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-07-30: 0.00%; 2023-10-01: RACK 기타 마감자재 8/1-9/30
|  | 5 | 2.1.1.8.1 |  |  |  |  | 단품 및 제작 |  | 2023-08-01 | 2023-09-30 | 60 | 305 | 0 | 61 | 0 |  |  |  | 0 | 5 |  |  | 0% | 0% | 2023-07-30: 0.00%; 2023-10-01: 단품 및 제작 8/1-9/30
| G | 4 | 2.1.1.9 |  |  |  | 고온#2 Aging (Deck&Accessory) |  |  | 2023-04-15 | 2023-08-30 |  | 751 | 0 | 138 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-04-09: 0.00%; 2023-08-27: 고온#2 Aging (Deck&Accessory) 4/15-8/30
|  | 5 | 2.1.1.9.1 |  |  |  |  | 단품 및 Post 생산/제작 | 5 | 2023-04-15 | 2023-07-30 | 106 | 535 | 0 | 107 | 0 |  |  |  | 0 | 5 |  |  | 0% | 0% | 2023-04-09: 0.00%; 2023-07-30: 단품 및 Post 생산/제작 4/15-7/30
|  | 5 | 2.1.1.9.2 |  |  |  |  | 1차조립 | 5 | 2023-05-15 | 2023-08-30 | 107 | 216 | 0 | 108 | 0 |  |  |  | 0 | 2 |  |  | 0% | 0% | 2023-05-14: 0.00%; 2023-08-27: 1차조립 5/15-8/30
| G | 4 | 2.1.1.10 |  |  |  | 상온#2 Aging (Deck&Accessory) |  |  | 2023-04-15 | 2023-08-30 |  | 751 | 0 | 138 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-04-09: 0.00%; 2023-08-27: 상온#2 Aging (Deck&Accessory) 4/15-8/30
|  | 5 | 2.1.1.10.1 |  |  |  |  | 단품 및 Post 생산/제작 | 6 | 2023-04-15 | 2023-07-30 | 106 | 535 | 0 | 107 | 0 |  |  |  | 0 | 5 |  |  | 0% | 0% | 2023-04-09: 0.00%; 2023-07-30: 단품 및 Post 생산/제작 4/15-7/30
|  | 5 | 2.1.1.10.2 |  |  |  |  | 1차조립 | 6 | 2023-05-15 | 2023-08-30 | 107 | 216 | 0 | 108 | 0 |  |  |  | 0 | 2 |  |  | 0% | 0% | 2023-05-14: 0.00%; 2023-08-27: 1차조립 5/15-8/30
| G | 4 | 2.1.1.11 |  |  |  | 공Tray Buffer |  |  | 2023-04-15 | 2023-08-30 |  | 751 | 0 | 138 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-04-09: 0.00%; 2023-08-27: 공Tray Buffer 4/15-8/30
|  | 5 | 2.1.1.11.1 |  |  |  |  | 단품 및 Post 생산/제작 | 6 | 2023-04-15 | 2023-07-30 | 106 | 535 | 0 | 107 | 0 |  |  |  | 0 | 5 |  |  | 0% | 0% | 2023-04-09: 0.00%; 2023-07-30: 단품 및 Post 생산/제작 4/15-7/30
|  | 5 | 2.1.1.11.2 |  |  |  |  | 1차조립 | 6 | 2023-05-15 | 2023-08-30 | 107 | 216 | 0 | 108 | 0 |  |  |  | 0 | 2 |  |  | 0% | 0% | 2023-05-14: 0.00%; 2023-08-27: 1차조립 5/15-8/30
| G | 4 | 2.1.1.12 |  |  |  | RACK 기타 마감자재 |  |  | 2023-08-01 | 2023-09-30 |  | 305 | 0 | 61 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-07-30: 0.00%; 2023-10-01: RACK 기타 마감자재 8/1-9/30
|  | 5 | 2.1.1.12.1 |  |  |  |  | 단품 및 제작 |  | 2023-08-01 | 2023-09-30 | 60 | 305 | 0 | 61 | 0 |  |  |  | 0 | 5 |  |  | 0% | 0% | 2023-07-30: 0.00%; 2023-10-01: 단품 및 제작 8/1-9/30
| G | 3 | 2.1.2 |  |  | MSC Crane(FR) |  |  |  | 2023-02-15 | 2023-11-30 |  | 9359 | 406 | 289 | 29 |  |  | 0 | 0 |  |  |  | 4.338% | 0% | 2023-02-12: 0.00%; 2023-11-26: MSC Crane(FR) 2/15-11/30
| G | 4 | 2.1.2.1 |  |  |  | 상온#1 Aging |  |  | 2023-02-15 | 2023-11-30 |  | 1337 | 58 | 289 | 29 |  |  | 0 | 0 |  |  |  | 4.338% | 0% | 2023-02-12: 0.00%; 2023-11-26: 상온#1 Aging 2/15-11/30
|  | 5 | 2.1.2.1.1 |  |  |  |  | 장납기 구매품 발주 및 입고 |  | 2023-02-15 | 2023-08-15 | 181 | 364 | 58 | 182 | 29 |  |  |  | 0 | 2 |  |  | 15.93% | 0% | 2023-02-12: 0.00%; 2023-08-13: 장납기 구매품 발주 및 입고 2/15-8/15
|  | 5 | 2.1.2.1.2 |  |  |  |  | 단품제작 |  | 2023-04-01 | 2023-07-30 | 120 | 363 | 0 | 121 | 0 |  |  |  | 0 | 3 |  |  | 0% | 0% | 2023-03-26: 0.00%; 2023-07-30: 단품제작 4/1-7/30
|  | 5 | 2.1.2.1.3 |  |  |  |  | 기구조립 |  | 2023-06-01 | 2023-09-30 | 121 | 488 | 0 | 122 | 0 |  |  |  | 0 | 4 |  |  | 0% | 0% | 2023-05-28: 0.00%; 2023-10-01: 기구조립 6/1-9/30
|  | 5 | 2.1.2.1.4 |  |  |  |  | 전장조립 |  | 2023-08-01 | 2023-11-30 | 121 | 122 | 0 | 122 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-07-30: 0.00%; 2023-11-26: 전장조립 8/1-11/30
| G | 4 | 2.1.2.2 |  |  |  | 고온#1 Aging |  |  | 2023-02-15 | 2023-11-30 |  | 1337 | 58 | 289 | 29 |  |  | 0 | 0 |  |  |  | 4.338% | 0% | 2023-02-12: 0.00%; 2023-11-26: 고온#1 Aging 2/15-11/30
|  | 5 | 2.1.2.2.1 |  |  |  |  | 장납기 구매품 발주 및 입고 |  | 2023-02-15 | 2023-08-15 | 181 | 364 | 58 | 182 | 29 |  |  |  | 0 | 2 |  |  | 15.93% | 0% | 2023-02-12: 0.00%; 2023-08-13: 장납기 구매품 발주 및 입고 2/15-8/15
|  | 5 | 2.1.2.2.2 |  |  |  |  | 단품제작 |  | 2023-04-01 | 2023-07-30 | 120 | 363 | 0 | 121 | 0 |  |  |  | 0 | 3 |  |  | 0% | 0% | 2023-03-26: 0.00%; 2023-07-30: 단품제작 4/1-7/30
|  | 5 | 2.1.2.2.3 |  |  |  |  | 기구조립 |  | 2023-06-01 | 2023-09-30 | 121 | 488 | 0 | 122 | 0 |  |  |  | 0 | 4 |  |  | 0% | 0% | 2023-05-28: 0.00%; 2023-10-01: 기구조립 6/1-9/30
|  | 5 | 2.1.2.2.4 |  |  |  |  | 전장조립 |  | 2023-08-01 | 2023-11-30 | 121 | 122 | 0 | 122 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-07-30: 0.00%; 2023-11-26: 전장조립 8/1-11/30
| G | 4 | 2.1.2.3 |  |  |  | PPC |  |  | 2023-02-15 | 2023-11-30 |  | 1337 | 58 | 289 | 29 |  |  | 0 | 0 |  |  |  | 4.338% | 0% | 2023-02-12: 0.00%; 2023-11-26: PPC 2/15-11/30
|  | 5 | 2.1.2.3.1 |  |  |  |  | 장납기 구매품 발주 및 입고 |  | 2023-02-15 | 2023-08-15 | 181 | 364 | 58 | 182 | 29 |  |  |  | 0 | 2 |  |  | 15.93% | 0% | 2023-02-12: 0.00%; 2023-08-13: 장납기 구매품 발주 및 입고 2/15-8/15
|  | 5 | 2.1.2.3.2 |  |  |  |  | 단품제작 |  | 2023-04-01 | 2023-07-30 | 120 | 363 | 0 | 121 | 0 |  |  |  | 0 | 3 |  |  | 0% | 0% | 2023-03-26: 0.00%; 2023-07-30: 단품제작 4/1-7/30
|  | 5 | 2.1.2.3.3 |  |  |  |  | 기구조립 |  | 2023-06-01 | 2023-09-30 | 121 | 488 | 0 | 122 | 0 |  |  |  | 0 | 4 |  |  | 0% | 0% | 2023-05-28: 0.00%; 2023-10-01: 기구조립 6/1-9/30
|  | 5 | 2.1.2.3.4 |  |  |  |  | 전장조립 |  | 2023-08-01 | 2023-11-30 | 121 | 122 | 0 | 122 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-07-30: 0.00%; 2023-11-26: 전장조립 8/1-11/30
| G | 4 | 2.1.2.4 |  |  |  | 충방전 |  |  | 2023-02-15 | 2023-11-30 |  | 1337 | 58 | 289 | 29 |  |  | 0 | 0 |  |  |  | 4.338% | 0% | 2023-02-12: 0.00%; 2023-11-26: 충방전 2/15-11/30
|  | 5 | 2.1.2.4.1 |  |  |  |  | 장납기 구매품 발주 및 입고 |  | 2023-02-15 | 2023-08-15 | 181 | 364 | 58 | 182 | 29 |  |  |  | 0 | 2 |  |  | 15.93% | 0% | 2023-02-12: 0.00%; 2023-08-13: 장납기 구매품 발주 및 입고 2/15-8/15
|  | 5 | 2.1.2.4.2 |  |  |  |  | 단품제작 |  | 2023-04-01 | 2023-07-30 | 120 | 363 | 0 | 121 | 0 |  |  |  | 0 | 3 |  |  | 0% | 0% | 2023-03-26: 0.00%; 2023-07-30: 단품제작 4/1-7/30
|  | 5 | 2.1.2.4.3 |  |  |  |  | 기구조립 |  | 2023-06-01 | 2023-09-30 | 121 | 488 | 0 | 122 | 0 |  |  |  | 0 | 4 |  |  | 0% | 0% | 2023-05-28: 0.00%; 2023-10-01: 기구조립 6/1-9/30
|  | 5 | 2.1.2.4.4 |  |  |  |  | 전장조립 |  | 2023-08-01 | 2023-11-30 | 121 | 122 | 0 | 122 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-07-30: 0.00%; 2023-11-26: 전장조립 8/1-11/30
| G | 4 | 2.1.2.5 |  |  |  | 고온#2 Aging |  |  | 2023-02-15 | 2023-11-30 |  | 1337 | 58 | 289 | 29 |  |  | 0 | 0 |  |  |  | 4.338% | 0% | 2023-02-12: 0.00%; 2023-11-26: 고온#2 Aging 2/15-11/30
|  | 5 | 2.1.2.5.1 |  |  |  |  | 장납기 구매품 발주 및 입고 |  | 2023-02-15 | 2023-08-15 | 181 | 364 | 58 | 182 | 29 |  |  |  | 0 | 2 |  |  | 15.93% | 0% | 2023-02-12: 0.00%; 2023-08-13: 장납기 구매품 발주 및 입고 2/15-8/15
|  | 5 | 2.1.2.5.2 |  |  |  |  | 단품제작 |  | 2023-04-01 | 2023-07-30 | 120 | 363 | 0 | 121 | 0 |  |  |  | 0 | 3 |  |  | 0% | 0% | 2023-03-26: 0.00%; 2023-07-30: 단품제작 4/1-7/30
|  | 5 | 2.1.2.5.3 |  |  |  |  | 기구조립 |  | 2023-06-01 | 2023-09-30 | 121 | 488 | 0 | 122 | 0 |  |  |  | 0 | 4 |  |  | 0% | 0% | 2023-05-28: 0.00%; 2023-10-01: 기구조립 6/1-9/30
|  | 5 | 2.1.2.5.4 |  |  |  |  | 전장조립 |  | 2023-08-01 | 2023-11-30 | 121 | 122 | 0 | 122 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-07-30: 0.00%; 2023-11-26: 전장조립 8/1-11/30
| G | 4 | 2.1.2.6 |  |  |  | 상온#2 Aging |  |  | 2023-02-15 | 2023-11-30 |  | 1337 | 58 | 289 | 29 |  |  | 0 | 0 |  |  |  | 4.338% | 0% | 2023-02-12: 0.00%; 2023-11-26: 상온#2 Aging 2/15-11/30
|  | 5 | 2.1.2.6.1 |  |  |  |  | 장납기 구매품 발주 및 입고 |  | 2023-02-15 | 2023-08-15 | 181 | 364 | 58 | 182 | 29 |  |  |  | 0 | 2 |  |  | 15.93% | 0% | 2023-02-12: 0.00%; 2023-08-13: 장납기 구매품 발주 및 입고 2/15-8/15
|  | 5 | 2.1.2.6.2 |  |  |  |  | 단품제작 |  | 2023-04-01 | 2023-07-30 | 120 | 363 | 0 | 121 | 0 |  |  |  | 0 | 3 |  |  | 0% | 0% | 2023-03-26: 0.00%; 2023-07-30: 단품제작 4/1-7/30
|  | 5 | 2.1.2.6.3 |  |  |  |  | 기구조립 |  | 2023-06-01 | 2023-09-30 | 121 | 488 | 0 | 122 | 0 |  |  |  | 0 | 4 |  |  | 0% | 0% | 2023-05-28: 0.00%; 2023-10-01: 기구조립 6/1-9/30
|  | 5 | 2.1.2.6.4 |  |  |  |  | 전장조립 |  | 2023-08-01 | 2023-11-30 | 121 | 122 | 0 | 122 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-07-30: 0.00%; 2023-11-26: 전장조립 8/1-11/30
| G | 4 | 2.1.2.7 |  |  |  | 공 Tray Buffer |  |  | 2023-02-15 | 2023-11-30 |  | 1337 | 58 | 289 | 29 |  |  | 0 | 0 |  |  |  | 4.338% | 0% | 2023-02-12: 0.00%; 2023-11-26: 공 Tray Buffer 2/15-11/30
|  | 5 | 2.1.2.7.1 |  |  |  |  | 장납기 구매품 발주 및 입고 |  | 2023-02-15 | 2023-08-15 | 181 | 364 | 58 | 182 | 29 |  |  |  | 0 | 2 |  |  | 15.93% | 0% | 2023-02-12: 0.00%; 2023-08-13: 장납기 구매품 발주 및 입고 2/15-8/15
|  | 5 | 2.1.2.7.2 |  |  |  |  | 단품제작 |  | 2023-04-01 | 2023-07-30 | 120 | 363 | 0 | 121 | 0 |  |  |  | 0 | 3 |  |  | 0% | 0% | 2023-03-26: 0.00%; 2023-07-30: 단품제작 4/1-7/30
|  | 5 | 2.1.2.7.3 |  |  |  |  | 기구조립 |  | 2023-06-01 | 2023-09-30 | 121 | 488 | 0 | 122 | 0 |  |  |  | 0 | 4 |  |  | 0% | 0% | 2023-05-28: 0.00%; 2023-10-01: 기구조립 6/1-9/30
|  | 5 | 2.1.2.7.4 |  |  |  |  | 전장조립 |  | 2023-08-01 | 2023-11-30 | 121 | 122 | 0 | 122 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-07-30: 0.00%; 2023-11-26: 전장조립 8/1-11/30
| G | 3 | 2.1.3 |  |  | Conveyor & Deck |  |  |  | 2023-02-15 | 2023-11-30 |  | 7876 | 406 | 289 | 29 |  |  | 0 | 0 |  |  |  | 5.155% | 0% | 2023-02-12: 0.00%; 2023-11-26: Conveyor & Deck 2/15-11/30
| G | 4 | 2.1.3.1 |  |  |  | 조립동 CV |  |  | 2023-02-15 | 2023-10-15 |  | 1100 | 58 | 243 | 29 |  |  | 0 | 0 |  |  |  | 5.273% | 0% | 2023-02-12: 0.00%; 2023-10-15: 조립동 CV 2/15-10/15
|  | 5 | 2.1.3.1.1 |  |  |  |  | 장납기 구매품 발주 및 입고 |  | 2023-02-15 | 2023-08-30 | 196 | 394 | 58 | 197 | 29 |  |  |  | 0 | 2 |  |  | 14.72% | 0% | 2023-02-12: 0.00%; 2023-08-27: 장납기 구매품 발주 및 입고 2/15-8/30
|  | 5 | 2.1.3.1.2 |  |  |  |  | 가공품 발주 및 입고 |  | 2023-04-01 | 2023-05-30 | 59 | 120 | 0 | 60 | 0 |  |  |  | 0 | 2 |  |  | 0% | 0% | 2023-03-26: 0.00%; 2023-05-28: 가공품 발주 및 입고 4/1-5/30
|  | 5 | 2.1.3.1.3 |  |  |  |  | 기구조립 |  | 2023-05-15 | 2023-09-15 | 123 | 496 | 0 | 124 | 0 |  |  |  | 0 | 4 |  |  | 0% | 0% | 2023-05-14: 0.00%; 2023-09-10: 기구조립 5/15-9/15
|  | 5 | 2.1.3.1.4 |  |  |  |  | 전장조립 |  | 2023-09-01 | 2023-10-15 | 44 | 90 | 0 | 45 | 0 |  |  |  | 0 | 2 |  |  | 0% | 0% | 2023-08-27: 0.00%; 2023-10-15: 전장조립 9/1-10/15
| G | 4 | 2.1.3.2 |  |  |  | 1F 상온#1,고온#1 Aging |  |  | 2023-02-15 | 2023-10-15 |  | 1100 | 58 | 243 | 29 |  |  | 0 | 0 |  |  |  | 5.273% | 0% | 2023-02-12: 0.00%; 2023-10-15: 1F 상온#1,고온#1 Aging 2/15-10/15
|  | 5 | 2.1.3.2.1 |  |  |  |  | 장납기 구매품 발주 및 입고 |  | 2023-02-15 | 2023-08-30 | 196 | 394 | 58 | 197 | 29 |  |  |  | 0 | 2 |  |  | 14.72% | 0% | 2023-02-12: 0.00%; 2023-08-27: 장납기 구매품 발주 및 입고 2/15-8/30
|  | 5 | 2.1.3.2.2 |  |  |  |  | 가공품 발주 및 입고 |  | 2023-04-01 | 2023-05-30 | 59 | 120 | 0 | 60 | 0 |  |  |  | 0 | 2 |  |  | 0% | 0% | 2023-03-26: 0.00%; 2023-05-28: 가공품 발주 및 입고 4/1-5/30
|  | 5 | 2.1.3.2.3 |  |  |  |  | 기구조립 |  | 2023-05-15 | 2023-09-15 | 123 | 496 | 0 | 124 | 0 |  |  |  | 0 | 4 |  |  | 0% | 0% | 2023-05-14: 0.00%; 2023-09-10: 기구조립 5/15-9/15
|  | 5 | 2.1.3.2.4 |  |  |  |  | 전장조립 |  | 2023-09-01 | 2023-10-15 | 44 | 90 | 0 | 45 | 0 |  |  |  | 0 | 2 |  |  | 0% | 0% | 2023-08-27: 0.00%; 2023-10-15: 전장조립 9/1-10/15
| G | 4 | 2.1.3.3 |  |  |  | 1F PPC CV |  |  | 2023-02-15 | 2023-10-15 |  | 1100 | 58 | 243 | 29 |  |  | 0 | 0 |  |  |  | 5.273% | 0% | 2023-02-12: 0.00%; 2023-10-15: 1F PPC CV 2/15-10/15
|  | 5 | 2.1.3.3.1 |  |  |  |  | 장납기 구매품 발주 및 입고 |  | 2023-02-15 | 2023-08-30 | 196 | 394 | 58 | 197 | 29 |  |  |  | 0 | 2 |  |  | 14.72% | 0% | 2023-02-12: 0.00%; 2023-08-27: 장납기 구매품 발주 및 입고 2/15-8/30
|  | 5 | 2.1.3.3.2 |  |  |  |  | 가공품 발주 및 입고 |  | 2023-04-01 | 2023-05-30 | 59 | 120 | 0 | 60 | 0 |  |  |  | 0 | 2 |  |  | 0% | 0% | 2023-03-26: 0.00%; 2023-05-28: 가공품 발주 및 입고 4/1-5/30
|  | 5 | 2.1.3.3.3 |  |  |  |  | 기구조립 |  | 2023-05-15 | 2023-09-15 | 123 | 496 | 0 | 124 | 0 |  |  |  | 0 | 4 |  |  | 0% | 0% | 2023-05-14: 0.00%; 2023-09-10: 기구조립 5/15-9/15
|  | 5 | 2.1.3.3.4 |  |  |  |  | 전장조립 |  | 2023-09-01 | 2023-10-15 | 44 | 90 | 0 | 45 | 0 |  |  |  | 0 | 2 |  |  | 0% | 0% | 2023-08-27: 0.00%; 2023-10-15: 전장조립 9/1-10/15
| G | 4 | 2.1.3.4 |  |  |  | 1F 충방전 CV |  |  | 2023-02-15 | 2023-11-30 |  | 1144 | 58 | 289 | 29 |  |  | 0 | 0 |  |  |  | 5.07% | 0% | 2023-02-12: 0.00%; 2023-11-26: 1F 충방전 CV 2/15-11/30
|  | 5 | 2.1.3.4.1 |  |  |  |  | 장납기 구매품 발주 및 입고 |  | 2023-02-15 | 2023-08-30 | 196 | 394 | 58 | 197 | 29 |  |  |  | 0 | 2 |  |  | 14.72% | 0% | 2023-02-12: 0.00%; 2023-08-27: 장납기 구매품 발주 및 입고 2/15-8/30
|  | 5 | 2.1.3.4.2 |  |  |  |  | 가공품 발주 및 입고 |  | 2023-04-15 | 2023-06-30 | 76 | 154 | 0 | 77 | 0 |  |  |  | 0 | 2 |  |  | 0% | 0% | 2023-04-09: 0.00%; 2023-06-25: 가공품 발주 및 입고 4/15-6/30
|  | 5 | 2.1.3.4.3 |  |  |  |  | 기구조립 |  | 2023-06-15 | 2023-10-15 | 122 | 492 | 0 | 123 | 0 |  |  |  | 0 | 4 |  |  | 0% | 0% | 2023-06-11: 0.00%; 2023-10-15: 기구조립 6/15-10/15
|  | 5 | 2.1.3.4.4 |  |  |  |  | 전장조립 |  | 2023-10-10 | 2023-11-30 | 51 | 104 | 0 | 52 | 0 |  |  |  | 0 | 2 |  |  | 0% | 0% | 2023-10-08: 0.00%; 2023-11-26: 전장조립 10/10-11/30
| G | 4 | 2.1.3.5 |  |  |  | 1F 고온#2, 상온#2 Aging (Folding CV) |  |  | 2023-02-15 | 2023-11-30 |  | 1144 | 58 | 289 | 29 |  |  | 0 | 0 |  |  |  | 5.07% | 0% | 2023-02-12: 0.00%; 2023-11-26: 1F 고온#2, 상온#2 Aging (Folding CV) 2/15-11/30
|  | 5 | 2.1.3.5.1 |  |  |  |  | 장납기 구매품 발주 및 입고 |  | 2023-02-15 | 2023-08-30 | 196 | 394 | 58 | 197 | 29 |  |  |  | 0 | 2 |  |  | 14.72% | 0% | 2023-02-12: 0.00%; 2023-08-27: 장납기 구매품 발주 및 입고 2/15-8/30
|  | 5 | 2.1.3.5.2 |  |  |  |  | 가공품 발주 및 입고 |  | 2023-04-15 | 2023-06-30 | 76 | 154 | 0 | 77 | 0 |  |  |  | 0 | 2 |  |  | 0% | 0% | 2023-04-09: 0.00%; 2023-06-25: 가공품 발주 및 입고 4/15-6/30
|  | 5 | 2.1.3.5.3 |  |  |  |  | 기구조립 |  | 2023-06-15 | 2023-10-15 | 122 | 492 | 0 | 123 | 0 |  |  |  | 0 | 4 |  |  | 0% | 0% | 2023-06-11: 0.00%; 2023-10-15: 기구조립 6/15-10/15
|  | 5 | 2.1.3.5.4 |  |  |  |  | 전장조립 |  | 2023-10-10 | 2023-11-30 | 51 | 104 | 0 | 52 | 0 |  |  |  | 0 | 2 |  |  | 0% | 0% | 2023-10-08: 0.00%; 2023-11-26: 전장조립 10/10-11/30
| G | 4 | 2.1.3.6 |  |  |  | 2F 상온#1, 고온#1 Aging (Degasssing CV) |  |  | 2023-02-15 | 2023-11-30 |  | 1144 | 58 | 289 | 29 |  |  | 0 | 0 |  |  |  | 5.07% | 0% | 2023-02-12: 0.00%; 2023-11-26: 2F 상온#1, 고온#1 Aging (Degasssing CV) 2/15-11/30
|  | 5 | 2.1.3.6.1 |  |  |  |  | 장납기 구매품 발주 및 입고 |  | 2023-02-15 | 2023-08-30 | 196 | 394 | 58 | 197 | 29 |  |  |  | 0 | 2 |  |  | 14.72% | 0% | 2023-02-12: 0.00%; 2023-08-27: 장납기 구매품 발주 및 입고 2/15-8/30
|  | 5 | 2.1.3.6.2 |  |  |  |  | 가공품 발주 및 입고 |  | 2023-04-15 | 2023-06-30 | 76 | 154 | 0 | 77 | 0 |  |  |  | 0 | 2 |  |  | 0% | 0% | 2023-04-09: 0.00%; 2023-06-25: 가공품 발주 및 입고 4/15-6/30
|  | 5 | 2.1.3.6.3 |  |  |  |  | 기구조립 |  | 2023-06-15 | 2023-10-15 | 122 | 492 | 0 | 123 | 0 |  |  |  | 0 | 4 |  |  | 0% | 0% | 2023-06-11: 0.00%; 2023-10-15: 기구조립 6/15-10/15
|  | 5 | 2.1.3.6.4 |  |  |  |  | 전장조립 |  | 2023-10-10 | 2023-11-30 | 51 | 104 | 0 | 52 | 0 |  |  |  | 0 | 2 |  |  | 0% | 0% | 2023-10-08: 0.00%; 2023-11-26: 전장조립 10/10-11/30
| G | 4 | 2.1.3.7 |  |  |  | 2F 고온#2, 상온#2 Aging (Degasssing CV) |  |  | 2023-02-15 | 2023-11-30 |  | 1144 | 58 | 289 | 29 |  |  | 0 | 0 |  |  |  | 5.07% | 0% | 2023-02-12: 0.00%; 2023-11-26: 2F 고온#2, 상온#2 Aging (Degasssing CV) 2/15-11/30
|  | 5 | 2.1.3.7.1 |  |  |  |  | 장납기 구매품 발주 및 입고 |  | 2023-02-15 | 2023-08-30 | 196 | 394 | 58 | 197 | 29 |  |  |  | 0 | 2 |  |  | 14.72% | 0% | 2023-02-12: 0.00%; 2023-08-27: 장납기 구매품 발주 및 입고 2/15-8/30
|  | 5 | 2.1.3.7.2 |  |  |  |  | 가공품 발주 및 입고 |  | 2023-04-15 | 2023-06-30 | 76 | 154 | 0 | 77 | 0 |  |  |  | 0 | 2 |  |  | 0% | 0% | 2023-04-09: 0.00%; 2023-06-25: 가공품 발주 및 입고 4/15-6/30
|  | 5 | 2.1.3.7.3 |  |  |  |  | 기구조립 |  | 2023-06-15 | 2023-10-15 | 122 | 492 | 0 | 123 | 0 |  |  |  | 0 | 4 |  |  | 0% | 0% | 2023-06-11: 0.00%; 2023-10-15: 기구조립 6/15-10/15
|  | 5 | 2.1.3.7.4 |  |  |  |  | 전장조립 |  | 2023-10-10 | 2023-11-30 | 51 | 104 | 0 | 52 | 0 |  |  |  | 0 | 2 |  |  | 0% | 0% | 2023-10-08: 0.00%; 2023-11-26: 전장조립 10/10-11/30
| G | 1 | 3 | FAT | [5 empty] | 2023-09-01 | 2023-11-30 |  | 393 | 0 | 91 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-08-27: 0.00%; 2023-11-26: FAT 9/1-11/30
| G | 2 | 3.1 |  | BOSK TN |  |  |  |  | 2023-09-01 | 2023-11-30 |  | 393 | 0 | 91 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-08-27: 0.00%; 2023-11-26: BOSK TN 9/1-11/30
| G | 3 | 3.1.1 |  |  | Rack |  |  |  | 2023-09-01 | 2023-09-30 |  | 30 | 0 | 30 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-08-27: 0.00%; 2023-10-01: Rack 9/1-9/30
| G | 4 | 3.1.1.1 |  |  |  | RACK & DECK |  |  | 2023-09-01 | 2023-09-30 |  | 30 | 0 | 30 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-08-27: 0.00%; 2023-10-01: RACK & DECK 9/1-9/30
|  | 5 | 3.1.1.1.1 |  |  |  |  | FAT |  | 2023-09-01 | 2023-09-30 | 29 | 30 | 0 | 30 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-08-27: 0.00%; 2023-10-01: FAT 9/1-9/30
| G | 3 | 3.1.2 |  |  | MSC Crane |  |  |  | 2023-09-01 | 2023-11-30 |  | 121 | 0 | 91 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-08-27: 0.00%; 2023-11-26: MSC Crane 9/1-11/30
| G | 4 | 3.1.2.1 |  |  |  | Aging+충방전 |  |  | 2023-09-01 | 2023-11-30 |  | 121 | 0 | 91 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-08-27: 0.00%; 2023-11-26: Aging+충방전 9/1-11/30
|  | 5 | 3.1.2.1.1 |  |  |  |  | 단동TEST |  | 2023-09-01 | 2023-11-30 | 90 | 91 | 0 | 91 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-08-27: 0.00%; 2023-11-26: 단동TEST 9/1-11/30
|  | 5 | 3.1.2.1.2 |  |  |  |  | FAT |  | 2023-10-01 | 2023-10-30 | 29 | 30 | 0 | 30 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-01: 0.00%; 2023-10-29: FAT 10/1-10/30
| G | 3 | 3.1.3 |  |  | 환적 이재기+PPC MSC |  |  |  | 2023-09-01 | 2023-11-30 |  | 121 | 0 | 91 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-08-27: 0.00%; 2023-11-26: 환적 이재기+PPC MSC 9/1-11/30
| G | 4 | 3.1.3.1 |  |  |  | 환적 이재기+PPC MSC |  |  | 2023-09-01 | 2023-11-30 |  | 121 | 0 | 91 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-08-27: 0.00%; 2023-11-26: 환적 이재기+PPC MSC 9/1-11/30
|  | 5 | 3.1.3.1.1 |  |  |  |  | 단동TEST |  | 2023-09-01 | 2023-11-30 | 90 | 91 | 0 | 91 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-08-27: 0.00%; 2023-11-26: 단동TEST 9/1-11/30
|  | 5 | 3.1.3.1.2 |  |  |  |  | FAT |  | 2023-10-01 | 2023-10-30 | 29 | 30 | 0 | 30 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-01: 0.00%; 2023-10-29: FAT 10/1-10/30
| G | 3 | 3.1.4 |  |  | Conveyor & Lifter |  |  |  | 2023-09-01 | 2023-11-30 |  | 121 | 0 | 91 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-08-27: 0.00%; 2023-11-26: Conveyor & Lifter 9/1-11/30
| G | 4 | 3.1.4.1 |  |  |  | Conveyor TEST & FAT |  |  | 2023-09-01 | 2023-11-30 |  | 121 | 0 | 91 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-08-27: 0.00%; 2023-11-26: Conveyor TEST & FAT 9/1-11/30
|  | 5 | 3.1.4.1.1 |  |  |  |  | 단동TEST |  | 2023-09-01 | 2023-11-30 | 90 | 91 | 0 | 91 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-08-27: 0.00%; 2023-11-26: 단동TEST 9/1-11/30
|  | 5 | 3.1.4.1.2 |  |  |  |  | FAT |  | 2023-10-01 | 2023-10-30 | 29 | 30 | 0 | 30 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-01: 0.00%; 2023-10-29: FAT 10/1-10/30
| G | 1 | 4 | FOB | [5 empty] | 2023-09-15 | 2024-02-01 |  | 389 | 0 | 140 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-09-10: 0.00%; 2024-01-28: FOB 9/15-2/1
| G | 2 | 4.1 |  | BOSK TN |  |  |  |  | 2023-09-15 | 2024-02-01 |  | 389 | 0 | 140 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-09-10: 0.00%; 2024-01-28: BOSK TN 9/15-2/1
| G | 3 | 4.1.1 |  |  | Rack |  |  |  | 2023-09-15 | 2024-01-19 |  | 196 | 0 | 127 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-09-10: 0.00%; 2024-01-14: Rack 9/15-1/19
| G | 4 | 4.1.1.1 |  |  |  | 1동 상온#1 Rack&Deck |  |  | 2023-09-15 | 2023-10-01 |  | 17 | 0 | 17 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-09-10: 0.00% 1동 상온#1 Rack&Deck 9/15-10/1
|  | 5 | 4.1.1.1.1 |  |  |  |  | Unit 포장 |  | 2023-09-15 | 2023-09-24 | 9 | 10 | 0 | 10 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-09-10: 0.00% Unit 포장 9/15-9/24
|  | 5 | 4.1.1.1.2 |  |  |  |  | Unit 운송 |  | 2023-09-25 | 2023-09-30 | 5 | 6 | 0 | 6 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-09-24: 0.00% Unit 운송 9/25-9/30
|  | 5 | 4.1.1.1.3 |  |  |  |  | FOB |  | 2023-10-01 | 2023-10-01 | 1 | 1 | 0 | 1 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-01: 0.00% FOB 10/1-10/1
|  | 5 | 4.1.1.1.4 |  |  |  |  | SHIPPING |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
|  | 5 | 4.1.1.1.5 |  |  |  |  | 하역 및 반입 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
| G | 4 | 4.1.1.2 |  |  |  | 1동 상온#2,3 Rack&Deck |  |  | 2023-09-15 | 2023-10-01 |  | 17 | 0 | 17 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-09-10: 0.00% 1동 상온#2,3 Rack&Deck 9/15-10/1
|  | 5 | 4.1.1.2.1 |  |  |  |  | Unit 포장 |  | 2023-09-15 | 2023-09-24 | 9 | 10 | 0 | 10 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-09-10: 0.00% Unit 포장 9/15-9/24
|  | 5 | 4.1.1.2.2 |  |  |  |  | Unit 운송 |  | 2023-09-25 | 2023-09-30 | 5 | 6 | 0 | 6 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-09-24: 0.00% Unit 운송 9/25-9/30
|  | 5 | 4.1.1.2.3 |  |  |  |  | FOB |  | 2023-10-01 | 2023-10-01 | 1 | 1 | 0 | 1 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-01: 0.00% FOB 10/1-10/1
|  | 5 | 4.1.1.2.4 |  |  |  |  | SHIPPING |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
|  | 5 | 4.1.1.2.5 |  |  |  |  | 하역 및 반입 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
| G | 4 | 4.1.1.3 |  |  |  | 1동 고온#1 Rack&Deck |  |  | 2023-10-10 | 2023-10-27 |  | 17 | 0 | 18 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-10-08: 0.00% 1동 고온#1 Rack&Deck 10/10-10/27
|  | 5 | 4.1.1.3.1 |  |  |  |  | Unit 포장 |  | 2023-10-10 | 2023-10-19 | 9 | 10 | 0 | 10 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-08: 0.00% Unit 포장 10/10-10/19
|  | 5 | 4.1.1.3.2 |  |  |  |  | Unit 운송 |  | 2023-10-20 | 2023-10-25 | 5 | 6 | 0 | 6 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-15: 0.00% Unit 운송 10/20-10/25
|  | 5 | 4.1.1.3.3 |  |  |  |  | FOB |  | 2023-10-27 | 2023-10-27 | 1 | 1 | 0 | 1 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-22: 0.00% FOB 10/27-10/27
|  | 5 | 4.1.1.3.4 |  |  |  |  | SHIPPING |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
|  | 5 | 4.1.1.3.5 |  |  |  |  | 하역 및 반입 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
| G | 4 | 4.1.1.4 |  |  |  | 1동 고온#2 Rack&Deck |  |  | 2023-10-10 | 2023-10-27 |  | 17 | 0 | 18 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-10-08: 0.00% 1동 고온#2 Rack&Deck 10/10-10/27
|  | 5 | 4.1.1.4.1 |  |  |  |  | Unit 포장 |  | 2023-10-10 | 2023-10-19 | 9 | 10 | 0 | 10 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-08: 0.00% Unit 포장 10/10-10/19
|  | 5 | 4.1.1.4.2 |  |  |  |  | Unit 운송 |  | 2023-10-20 | 2023-10-25 | 5 | 6 | 0 | 6 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-15: 0.00% Unit 운송 10/20-10/25
|  | 5 | 4.1.1.4.3 |  |  |  |  | FOB |  | 2023-10-27 | 2023-10-27 | 1 | 1 | 0 | 1 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-22: 0.00% FOB 10/27-10/27
|  | 5 | 4.1.1.4.4 |  |  |  |  | SHIPPING |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
|  | 5 | 4.1.1.4.5 |  |  |  |  | 하역 및 반입 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
| G | 4 | 4.1.1.5 |  |  |  | 1동 PPC,충방전 Rack&Deck |  |  | 2023-10-10 | 2023-10-27 |  | 17 | 0 | 18 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-10-08: 0.00% 1동 PPC,충방전 Rack&Deck 10/10-10/27
|  | 5 | 4.1.1.5.1 |  |  |  |  | Unit 포장 |  | 2023-10-10 | 2023-10-19 | 9 | 10 | 0 | 10 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-08: 0.00% Unit 포장 10/10-10/19
|  | 5 | 4.1.1.5.2 |  |  |  |  | Unit 운송 |  | 2023-10-20 | 2023-10-25 | 5 | 6 | 0 | 6 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-15: 0.00% Unit 운송 10/20-10/25
|  | 5 | 4.1.1.5.3 |  |  |  |  | FOB |  | 2023-10-27 | 2023-10-27 | 1 | 1 | 0 | 1 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-22: 0.00% FOB 10/27-10/27
|  | 5 | 4.1.1.5.4 |  |  |  |  | SHIPPING |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
|  | 5 | 4.1.1.5.5 |  |  |  |  | 하역 및 반입 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
| G | 4 | 4.1.1.6 |  |  |  | 1동 공Tray Rack&Deck |  |  | 2023-10-10 | 2023-10-27 |  | 17 | 0 | 18 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-10-08: 0.00% 1동 공Tray Rack&Deck 10/10-10/27
|  | 5 | 4.1.1.6.1 |  |  |  |  | Unit 포장 |  | 2023-10-10 | 2023-10-19 | 9 | 10 | 0 | 10 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-08: 0.00% Unit 포장 10/10-10/19
|  | 5 | 4.1.1.6.2 |  |  |  |  | Unit 운송 |  | 2023-10-20 | 2023-10-25 | 5 | 6 | 0 | 6 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-15: 0.00% Unit 운송 10/20-10/25
|  | 5 | 4.1.1.6.3 |  |  |  |  | FOB |  | 2023-10-27 | 2023-10-27 | 1 | 1 | 0 | 1 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-22: 0.00% FOB 10/27-10/27
|  | 5 | 4.1.1.6.4 |  |  |  |  | SHIPPING |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
|  | 5 | 4.1.1.6.5 |  |  |  |  | 하역 및 반입 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
| G | 4 | 4.1.1.7 |  |  |  | 2동 상온#1 Rack&Deck |  |  | 2023-12-15 | 2024-01-03 |  | 17 | 0 | 20 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-12-10: 0.00% 2동 상온#1 Rack&Deck 12/15-1/3
|  | 5 | 4.1.1.7.1 |  |  |  |  | Unit 포장 |  | 2023-12-15 | 2023-12-25 | 10 | 11 | 0 | 11 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-12-10: 0.00% Unit 포장 12/15-12/25
|  | 5 | 4.1.1.7.2 |  |  |  |  | Unit 운송 |  | 2023-12-26 | 2023-12-30 | 4 | 5 | 0 | 5 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-12-24: 0.00% Unit 운송 12/26-12/30
|  | 5 | 4.1.1.7.3 |  |  |  |  | FOB |  | 2024-01-03 | 2024-01-03 | 1 | 1 | 0 | 1 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-12-31: 0.00% FOB 1/3-1/3
|  | 5 | 4.1.1.7.4 |  |  |  |  | SHIPPING |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
|  | 5 | 4.1.1.7.5 |  |  |  |  | 하역 및 반입 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
| G | 4 | 4.1.1.8 |  |  |  | 2동 상온#2,3 Rack&Deck |  |  | 2023-12-15 | 2024-01-03 |  | 17 | 0 | 20 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-12-10: 0.00% 2동 상온#2,3 Rack&Deck 12/15-1/3
|  | 5 | 4.1.1.8.1 |  |  |  |  | Unit 포장 |  | 2023-12-15 | 2023-12-25 | 10 | 11 | 0 | 11 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-12-10: 0.00% Unit 포장 12/15-12/25
|  | 5 | 4.1.1.8.2 |  |  |  |  | Unit 운송 |  | 2023-12-26 | 2023-12-30 | 4 | 5 | 0 | 5 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-12-24: 0.00% Unit 운송 12/26-12/30
|  | 5 | 4.1.1.8.3 |  |  |  |  | FOB |  | 2024-01-03 | 2024-01-03 | 1 | 1 | 0 | 1 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-12-31: 0.00% FOB 1/3-1/3
|  | 5 | 4.1.1.8.4 |  |  |  |  | SHIPPING |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
|  | 5 | 4.1.1.8.5 |  |  |  |  | 하역 및 반입 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
| G | 4 | 4.1.1.9 |  |  |  | 2동 고온#1 Rack&Deck |  |  | 2024-01-05 | 2024-01-19 |  | 15 | 0 | 15 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-12-31: 0.00% 2동 고온#1 Rack&Deck 1/5-1/19
|  | 5 | 4.1.1.9.1 |  |  |  |  | Unit 포장 |  | 2024-01-05 | 2024-01-13 | 8 | 9 | 0 | 9 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-12-31: 0.00% Unit 포장 1/5-1/13
|  | 5 | 4.1.1.9.2 |  |  |  |  | Unit 운송 |  | 2024-01-14 | 2024-01-18 | 4 | 5 | 0 | 5 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2024-01-14: 0.00% Unit 운송 1/14-1/18
|  | 5 | 4.1.1.9.3 |  |  |  |  | FOB |  | 2024-01-19 | 2024-01-19 | 1 | 1 | 0 | 1 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2024-01-14: 0.00% FOB 1/19-1/19
|  | 5 | 4.1.1.9.4 |  |  |  |  | SHIPPING |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
|  | 5 | 4.1.1.9.5 |  |  |  |  | 하역 및 반입 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
| G | 4 | 4.1.1.10 |  |  |  | 2동 고온#2 Rack |  |  | 2024-01-05 | 2024-01-19 |  | 15 | 0 | 15 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-12-31: 0.00% 2동 고온#2 Rack 1/5-1/19
|  | 5 | 4.1.1.10.1 |  |  |  |  | Unit 포장 |  | 2024-01-05 | 2024-01-13 | 8 | 9 | 0 | 9 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-12-31: 0.00% Unit 포장 1/5-1/13
|  | 5 | 4.1.1.10.2 |  |  |  |  | Unit 운송 |  | 2024-01-14 | 2024-01-18 | 4 | 5 | 0 | 5 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2024-01-14: 0.00% Unit 운송 1/14-1/18
|  | 5 | 4.1.1.10.3 |  |  |  |  | FOB |  | 2024-01-19 | 2024-01-19 | 1 | 1 | 0 | 1 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2024-01-14: 0.00% FOB 1/19-1/19
|  | 5 | 4.1.1.10.4 |  |  |  |  | SHIPPING |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
|  | 5 | 4.1.1.10.5 |  |  |  |  | 하역 및 반입 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
| G | 4 | 4.1.1.11 |  |  |  | 2동 PPC,충방전 Rack&Deck |  |  | 2024-01-05 | 2024-01-19 |  | 15 | 0 | 15 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-12-31: 0.00% 2동 PPC,충방전 Rack&Deck 1/5-1/19
|  | 5 | 4.1.1.11.1 |  |  |  |  | Unit 포장 |  | 2024-01-05 | 2024-01-13 | 8 | 9 | 0 | 9 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-12-31: 0.00% Unit 포장 1/5-1/13
|  | 5 | 4.1.1.11.2 |  |  |  |  | Unit 운송 |  | 2024-01-14 | 2024-01-18 | 4 | 5 | 0 | 5 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2024-01-14: 0.00% Unit 운송 1/14-1/18
|  | 5 | 4.1.1.11.3 |  |  |  |  | FOB |  | 2024-01-19 | 2024-01-19 | 1 | 1 | 0 | 1 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2024-01-14: 0.00% FOB 1/19-1/19
|  | 5 | 4.1.1.11.4 |  |  |  |  | SHIPPING |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
|  | 5 | 4.1.1.11.5 |  |  |  |  | 하역 및 반입 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
| G | 4 | 4.1.1.12 |  |  |  | 2동 공tray Rack&Deck |  |  | 2024-01-05 | 2024-01-19 |  | 15 | 0 | 15 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-12-31: 0.00% 2동 공tray Rack&Deck 1/5-1/19
|  | 5 | 4.1.1.12.1 |  |  |  |  | Unit 포장 |  | 2024-01-05 | 2024-01-13 | 8 | 9 | 0 | 9 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-12-31: 0.00% Unit 포장 1/5-1/13
|  | 5 | 4.1.1.12.2 |  |  |  |  | Unit 운송 |  | 2024-01-14 | 2024-01-18 | 4 | 5 | 0 | 5 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2024-01-14: 0.00% Unit 운송 1/14-1/18
|  | 5 | 4.1.1.12.3 |  |  |  |  | FOB |  | 2024-01-19 | 2024-01-19 | 1 | 1 | 0 | 1 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2024-01-14: 0.00% FOB 1/19-1/19
|  | 5 | 4.1.1.12.4 |  |  |  |  | SHIPPING |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
|  | 5 | 4.1.1.12.5 |  |  |  |  | 하역 및 반입 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
| G | 3 | 4.1.2 |  |  | MSC Crane(FR) |  |  |  | 2023-11-01 | 2024-02-01 |  | 33 | 0 | 93 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-10-29: 0.00%; 2024-01-28: MSC Crane(FR) 11/1-2/1
| G | 4 | 4.1.2.1 |  |  |  | 1동 Aging,PPC,충방,공Tray MSC |  |  | 2023-11-01 | 2023-11-15 |  | 16 | 0 | 15 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-10-29: 0.00% 1동 Aging,PPC,충방,공Tray MSC 11/1-11/15
|  | 5 | 4.1.2.1.1 |  |  |  |  | Unit 포장 |  | 2023-11-01 | 2023-11-10 | 9 | 10 | 0 | 10 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-29: 0.00% Unit 포장 11/1-11/10
|  | 5 | 4.1.2.1.2 |  |  |  |  | Unit 운송 |  | 2023-11-10 | 2023-11-14 | 4 | 5 | 0 | 5 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-11-05: 0.00% Unit 운송 11/10-11/14
|  | 5 | 4.1.2.1.3 |  |  |  |  | FOB |  | 2023-11-15 | 2023-11-15 | 1 | 1 | 0 | 1 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-11-12: 0.00% FOB 11/15-11/15
|  | 5 | 4.1.2.1.4 |  |  |  |  | SHIPPING |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
|  | 5 | 4.1.2.1.5 |  |  |  |  | 하역 및 반입 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
| G | 4 | 4.1.2.2 |  |  |  | 2동 Aging,PPC,충방,공Tray MSC |  |  | 2024-01-15 | 2024-02-01 |  | 17 | 0 | 18 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2024-01-14: 0.00% 2동 Aging,PPC,충방,공Tray MSC 1/15-2/1
|  | 5 | 4.1.2.2.1 |  |  |  |  | Unit 포장 |  | 2024-01-15 | 2024-01-24 | 9 | 10 | 0 | 10 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2024-01-14: 0.00% Unit 포장 1/15-1/24
|  | 5 | 4.1.2.2.2 |  |  |  |  | Unit 운송 |  | 2024-01-25 | 2024-01-30 | 5 | 6 | 0 | 6 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2024-01-21: 0.00% Unit 운송 1/25-1/30
|  | 5 | 4.1.2.2.3 |  |  |  |  | FOB |  | 2024-02-01 | 2024-02-01 | 1 | 1 | 0 | 1 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2024-01-28: 0.00% FOB 2/1-2/1
|  | 5 | 4.1.2.2.4 |  |  |  |  | SHIPPING |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
|  | 5 | 4.1.2.2.5 |  |  |  |  | 하역 및 반입 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
| G | 3 | 4.1.3 |  |  | Conveyor & Deck (해당구역 L/F포함 일정) |  |  |  | 2023-10-10 | 2024-01-19 |  | 160 | 0 | 102 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-10-08: 0.00%; 2024-01-14: Conveyor & Deck (해당구역 L/F포함 일정) 10/10-1/19
| G | 4 | 4.1.3.1 |  |  |  | 1동 조립동CV |  |  | 2023-10-10 | 2023-10-27 |  | 17 | 0 | 18 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-10-08: 0.00% 1동 조립동CV 10/10-10/27
|  | 5 | 4.1.3.1.1 |  |  |  |  | Unit 포장 |  | 2023-10-10 | 2023-10-19 | 9 | 10 | 0 | 10 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-08: 0.00% Unit 포장 10/10-10/19
|  | 5 | 4.1.3.1.2 |  |  |  |  | Unit 운송 |  | 2023-10-20 | 2023-10-25 | 5 | 6 | 0 | 6 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-15: 0.00% Unit 운송 10/20-10/25
|  | 5 | 4.1.3.1.3 |  |  |  |  | FOB |  | 2023-10-27 | 2023-10-27 | 1 | 1 | 0 | 1 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-22: 0.00% FOB 10/27-10/27
|  | 5 | 4.1.3.1.4 |  |  |  |  | SHIPPING |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
|  | 5 | 4.1.3.1.5 |  |  |  |  | 하역 및 반입 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
| G | 4 | 4.1.3.2 |  |  |  | 1F 동간물류CV |  |  | 2023-10-10 | 2023-10-27 |  | 17 | 0 | 18 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-10-08: 0.00% 1F 동간물류CV 10/10-10/27
|  | 5 | 4.1.3.2.1 |  |  |  |  | Unit 포장 |  | 2023-10-10 | 2023-10-19 | 9 | 10 | 0 | 10 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-08: 0.00% Unit 포장 10/10-10/19
|  | 5 | 4.1.3.2.2 |  |  |  |  | Unit 운송 |  | 2023-10-20 | 2023-10-25 | 5 | 6 | 0 | 6 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-15: 0.00% Unit 운송 10/20-10/25
|  | 5 | 4.1.3.2.3 |  |  |  |  | FOB(창고내 내 Deck 우선) |  | 2023-10-27 | 2023-10-27 | 1 | 1 | 0 | 1 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-22: 0.00% FOB(창고내 내 Deck 우선) 10/27-10/27
|  | 5 | 4.1.3.2.4 |  |  |  |  | SHIPPING |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
|  | 5 | 4.1.3.2.5 |  |  |  |  | 하역 및 반입 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
| G | 4 | 4.1.3.3 |  |  |  | 1동 Aging,PPC,충방창고CV |  |  | 2023-10-10 | 2023-10-27 |  | 17 | 0 | 18 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-10-08: 0.00% 1동 Aging,PPC,충방창고CV 10/10-10/27
|  | 5 | 4.1.3.3.1 |  |  |  |  | Unit 포장 |  | 2023-10-10 | 2023-10-19 | 9 | 10 | 0 | 10 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-08: 0.00% Unit 포장 10/10-10/19
|  | 5 | 4.1.3.3.2 |  |  |  |  | Unit 운송 |  | 2023-10-20 | 2023-10-25 | 5 | 6 | 0 | 6 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-15: 0.00% Unit 운송 10/20-10/25
|  | 5 | 4.1.3.3.3 |  |  |  |  | FOB(창고내 내 Deck 우선) |  | 2023-10-27 | 2023-10-27 | 1 | 1 | 0 | 1 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-22: 0.00% FOB(창고내 내 Deck 우선) 10/27-10/27
|  | 5 | 4.1.3.3.4 |  |  |  |  | SHIPPING |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
|  | 5 | 4.1.3.3.5 |  |  |  |  | 하역 및 반입 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
| G | 4 | 4.1.3.4 |  |  |  | 1동 Folding CV |  |  | 2023-10-10 | 2023-10-27 |  | 17 | 0 | 18 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-10-08: 0.00% 1동 Folding CV 10/10-10/27
|  | 5 | 4.1.3.4.1 |  |  |  |  | Unit 포장 |  | 2023-10-10 | 2023-10-19 | 9 | 10 | 0 | 10 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-08: 0.00% Unit 포장 10/10-10/19
|  | 5 | 4.1.3.4.2 |  |  |  |  | Unit 운송 |  | 2023-10-20 | 2023-10-25 | 5 | 6 | 0 | 6 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-15: 0.00% Unit 운송 10/20-10/25
|  | 5 | 4.1.3.4.3 |  |  |  |  | FOB(창고내 내 Deck 우선) |  | 2023-10-27 | 2023-10-27 | 1 | 1 | 0 | 1 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-22: 0.00% FOB(창고내 내 Deck 우선) 10/27-10/27
|  | 5 | 4.1.3.4.4 |  |  |  |  | SHIPPING |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
|  | 5 | 4.1.3.4.5 |  |  |  |  | 하역 및 반입 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
| G | 4 | 4.1.3.5 |  |  |  | 1동 Degassing CV |  |  | 2023-10-10 | 2023-10-27 |  | 17 | 0 | 18 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-10-08: 0.00% 1동 Degassing CV 10/10-10/27
|  | 5 | 4.1.3.5.1 |  |  |  |  | Unit 포장 |  | 2023-10-10 | 2023-10-19 | 9 | 10 | 0 | 10 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-08: 0.00% Unit 포장 10/10-10/19
|  | 5 | 4.1.3.5.2 |  |  |  |  | Unit 운송 |  | 2023-10-20 | 2023-10-25 | 5 | 6 | 0 | 6 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-15: 0.00% Unit 운송 10/20-10/25
|  | 5 | 4.1.3.5.3 |  |  |  |  | FOB(창고내 내 Deck 우선) |  | 2023-10-27 | 2023-10-27 | 1 | 1 | 0 | 1 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-10-22: 0.00% FOB(창고내 내 Deck 우선) 10/27-10/27
|  | 5 | 4.1.3.5.4 |  |  |  |  | SHIPPING |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
|  | 5 | 4.1.3.5.5 |  |  |  |  | 하역 및 반입 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
| G | 4 | 4.1.3.6 |  |  |  | 2동 조립동CV |  |  | 2024-01-05 | 2024-01-19 |  | 15 | 0 | 15 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-12-31: 0.00% 2동 조립동CV 1/5-1/19
|  | 5 | 4.1.3.6.1 |  |  |  |  | Unit 포장 |  | 2024-01-05 | 2024-01-13 | 8 | 9 | 0 | 9 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-12-31: 0.00% Unit 포장 1/5-1/13
|  | 5 | 4.1.3.6.2 |  |  |  |  | Unit 운송 |  | 2024-01-14 | 2024-01-18 | 4 | 5 | 0 | 5 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2024-01-14: 0.00% Unit 운송 1/14-1/18
|  | 5 | 4.1.3.6.3 |  |  |  |  | FOB |  | 2024-01-19 | 2024-01-19 | 1 | 1 | 0 | 1 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2024-01-14: 0.00% FOB 1/19-1/19
|  | 5 | 4.1.3.6.4 |  |  |  |  | SHIPPING |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
|  | 5 | 4.1.3.6.5 |  |  |  |  | 하역 및 반입 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
| G | 4 | 4.1.3.7 |  |  |  | 2F 동간물류CV |  |  | 2024-01-05 | 2024-01-19 |  | 15 | 0 | 15 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-12-31: 0.00% 2F 동간물류CV 1/5-1/19
|  | 5 | 4.1.3.7.1 |  |  |  |  | Unit 포장 |  | 2024-01-05 | 2024-01-13 | 8 | 9 | 0 | 9 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-12-31: 0.00% Unit 포장 1/5-1/13
|  | 5 | 4.1.3.7.2 |  |  |  |  | Unit 운송 |  | 2024-01-14 | 2024-01-18 | 4 | 5 | 0 | 5 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2024-01-14: 0.00% Unit 운송 1/14-1/18
|  | 5 | 4.1.3.7.3 |  |  |  |  | FOB(창고내 내 Deck 우선) |  | 2024-01-19 | 2024-01-19 | 1 | 1 | 0 | 1 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2024-01-14: 0.00% FOB(창고내 내 Deck 우선) 1/19-1/19
|  | 5 | 4.1.3.7.4 |  |  |  |  | SHIPPING |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
|  | 5 | 4.1.3.7.5 |  |  |  |  | 하역 및 반입 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
| G | 4 | 4.1.3.8 |  |  |  | 2동 Aging,PPC,충방창고CV |  |  | 2024-01-05 | 2024-01-19 |  | 15 | 0 | 15 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-12-31: 0.00% 2동 Aging,PPC,충방창고CV 1/5-1/19
|  | 5 | 4.1.3.8.1 |  |  |  |  | Unit 포장 |  | 2024-01-05 | 2024-01-13 | 8 | 9 | 0 | 9 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-12-31: 0.00% Unit 포장 1/5-1/13
|  | 5 | 4.1.3.8.2 |  |  |  |  | Unit 운송 |  | 2024-01-14 | 2024-01-18 | 4 | 5 | 0 | 5 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2024-01-14: 0.00% Unit 운송 1/14-1/18
|  | 5 | 4.1.3.8.3 |  |  |  |  | FOB(창고내 내 Deck 우선) |  | 2024-01-19 | 2024-01-19 | 1 | 1 | 0 | 1 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2024-01-14: 0.00% FOB(창고내 내 Deck 우선) 1/19-1/19
|  | 5 | 4.1.3.8.4 |  |  |  |  | SHIPPING |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
|  | 5 | 4.1.3.8.5 |  |  |  |  | 하역 및 반입 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
| G | 4 | 4.1.3.9 |  |  |  | 2동 Folding CV |  |  | 2024-01-05 | 2024-01-19 |  | 15 | 0 | 15 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-12-31: 0.00% 2동 Folding CV 1/5-1/19
|  | 5 | 4.1.3.9.1 |  |  |  |  | Unit 포장 |  | 2024-01-05 | 2024-01-13 | 8 | 9 | 0 | 9 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-12-31: 0.00% Unit 포장 1/5-1/13
|  | 5 | 4.1.3.9.2 |  |  |  |  | Unit 운송 |  | 2024-01-14 | 2024-01-18 | 4 | 5 | 0 | 5 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2024-01-14: 0.00% Unit 운송 1/14-1/18
|  | 5 | 4.1.3.9.3 |  |  |  |  | FOB(창고내 내 Deck 우선) |  | 2024-01-19 | 2024-01-19 | 1 | 1 | 0 | 1 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2024-01-14: 0.00% FOB(창고내 내 Deck 우선) 1/19-1/19
|  | 5 | 4.1.3.9.4 |  |  |  |  | SHIPPING |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
|  | 5 | 4.1.3.9.5 |  |  |  |  | 하역 및 반입 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
| G | 4 | 4.1.3.10 |  |  |  | 2동 Degassing CV |  |  | 2024-01-05 | 2024-01-19 |  | 15 | 0 | 15 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-12-31: 0.00% 2동 Degassing CV 1/5-1/19
|  | 5 | 4.1.3.10.1 |  |  |  |  | Unit 포장 |  | 2024-01-05 | 2024-01-13 | 8 | 9 | 0 | 9 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2023-12-31: 0.00% Unit 포장 1/5-1/13
|  | 5 | 4.1.3.10.2 |  |  |  |  | Unit 운송 |  | 2024-01-14 | 2024-01-18 | 4 | 5 | 0 | 5 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2024-01-14: 0.00% Unit 운송 1/14-1/18
|  | 5 | 4.1.3.10.3 |  |  |  |  | FOB(창고내 내 Deck 우선) |  | 2024-01-19 | 2024-01-19 | 1 | 1 | 0 | 1 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2024-01-14: 0.00% FOB(창고내 내 Deck 우선) 1/19-1/19
|  | 5 | 4.1.3.10.4 |  |  |  |  | SHIPPING |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
|  | 5 | 4.1.3.10.5 |  |  |  |  | 하역 및 반입 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 |  |  | 0% | 0%
| G | 1 | 5 | SETUP | [8 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2023-12-03: 12/03 W49; 2023-12-31: 12/31 W53; 2024-01-28: 2024 W5; 2024-02-25: 02/25 W9; 2024-03-24: 03/24 W13; 2024-04-21: 04/21 W17; 2024-05-19: 05/19 W21; 2024-06-16: 06/16 W25; 2024-07-14: 07/14 W29
| G | 1 | 1 | Installation |  |  |  |  | Installation | [16 empty] | 2024-02-04: 0.00%; 2024-08-04: Installation
| G | 2 | 1.1 |  | Cathode |  |  |  | Cathode | [16 empty] | 2024-02-04: 0.00%; 2024-08-04: Cathode
| G | 3 | 1.1.1 |  |  | PPC Room |  |  | CA-PPC | [16 empty] | 2024-01-28: 0.00%; 2024-04-21: PPC Room
|  | 4 | 1.1.1.1 |  |  |  | Line Marking |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-01-28: 0.00% Line Marking
|  | 4 | 1.1.1.2 |  |  |  | Check Floor Level |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Check Floor Level
|  | 4 | 1.1.1.3 |  |  |  | Check Line Marking |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Check Line Marking
|  | 4 | 1.1.1.4 |  |  |  | Drilling Anchor Hole |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Drilling Anchor Hole
|  | 4 | 1.1.1.5 |  |  |  | Move In |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00%; 2024-04-21: Move In
|  | 4 | 1.1.1.6 |  |  |  | Install Anchor & Nut |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Install Anchor & Nut
|  | 4 | 1.1.1.7 |  |  |  | Install Deck Post&Girder&Bracing |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Install Deck Post&Girder&Bracing
|  | 4 | 1.1.1.8 |  |  |  | Install Tower Stair |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Tower Stair
|  | 4 | 1.1.1.9 |  |  |  | Check Vertical(Deck Post&Tower Stair) |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Check Vertical(Deck Post&Tower Stair)
|  | 4 | 1.1.1.10 |  |  |  | Install Deck Frame&Hand Rail |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Deck Frame&Hand Rail
|  | 4 | 1.1.1.11 |  |  |  | Check Track Number |  | Lifter | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Check Track Number
|  | 4 | 1.1.1.12 |  |  |  | Install Lifter |  | Lifter | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Lifter
|  | 4 | 1.1.1.13 |  |  |  | Check Vertical |  | Lifter | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Check Vertical
|  | 4 | 1.1.1.14 |  |  |  | Setting Lifter Driving Accessories |  | Lifter | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Setting Lifter Driving Accessories
|  | 4 | 1.1.1.15 |  |  |  | Install Anchor |  | Lifter | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Anchor
|  | 4 | 1.1.1.16 |  |  |  | Install Anchor & Nut |  | deck(Transfer & CV) | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Anchor & Nut
|  | 4 | 1.1.1.17 |  |  |  | Check Nut Level |  | deck(Transfer & CV) | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Check Nut Level
|  | 4 | 1.1.1.18 |  |  |  | Install Deck Post&Girder(Floor 1~3) |  | deck(Transfer & CV) | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Deck Post&Girder(Floor 1~3)
|  | 4 | 1.1.1.19 |  |  |  | Install Rail Base(Floor 1~3) |  | deck(Transfer & CV) | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Rail Base(Floor 1~3)
|  | 4 | 1.1.1.20 |  |  |  | Check Rail Base Level |  | deck(Transfer & CV) | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Check Rail Base Level
|  | 4 | 1.1.1.21 |  |  |  | Install Deck Frame(Floor 2, Floor 3_80%) |  | deck(Transfer & CV) | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Install Deck Frame(Floor 2, Floor 3_80%)
|  | 4 | 1.1.1.22 |  |  |  | Check Track Number |  | Transfer&C/V | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Check Track Number
|  | 4 | 1.1.1.23 |  |  |  | Install Transfer & C/V(Floor 2) |  | Transfer&C/V | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Install Transfer & C/V(Floor 2)
|  | 4 | 1.1.1.24 |  |  |  | Install Compete Deck Frame(Floor 3) |  | deck(Transfer & CV) | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Install Compete Deck Frame(Floor 3)
|  | 4 | 1.1.1.25 |  |  |  | Install Transfer & C/V(Floor 3) |  | Transfer&C/V | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Install Transfer & C/V(Floor 3)
|  | 4 | 1.1.1.26 |  |  |  | Install Transfer & C/V(Floor 1) |  | Transfer&C/V | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Install Transfer & C/V(Floor 1)
|  | 4 | 1.1.1.27 |  |  |  | Check Center Line |  | Transfer&C/V | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Check Center Line
|  | 4 | 1.1.1.28 |  |  |  | Check C/V Level |  | Transfer&C/V | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Check C/V Level
|  | 4 | 1.1.1.29 |  |  |  | Install Anchor |  | Transfer&C/V | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Install Anchor
|  | 4 | 1.1.1.30 |  |  |  | Install Fence & Top Cover(Transfer) |  | Transfer&C/V | [11 empty] | 1 |  |  |  |  | 2024-03-24: 0.00% Install Fence & Top Cover(Transfer)
|  | 4 | 1.1.1.31 |  |  |  | Install Under Rail & Top Rail |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Install Under Rail & Top Rail
|  | 4 | 1.1.1.32 |  |  |  | Check Leveling(U.R & T.R) |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Check Leveling(U.R & T.R)
|  | 4 | 1.1.1.33 |  |  |  | Check Center Line |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-24: 0.00% Check Center Line
|  | 4 | 1.1.1.34 |  |  |  | Install MSC |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-24: 0.00% Install MSC
|  | 4 | 1.1.1.35 |  |  |  | Install MSC Aceessories |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-24: 0.00% Install MSC Aceessories
|  | 4 | 1.1.1.36 |  |  |  | Install Water Tank |  | etc | [11 empty] | 1 |  |  |  |  | 2024-03-31: 0.00% Install Water Tank
|  | 4 | 1.1.1.37 |  |  |  | Grouting & Cleaning |  | etc | [11 empty] | 1 |  |  |  |  | 2024-03-31: 0.00% Grouting & Cleaning
| G | 3 | 1.1.2 |  |  | Charger Room |  |  | CA-FCH | [16 empty] | 2024-01-14: 0.00%; 2024-04-21: Charger Room
|  | 4 | 1.1.2.1 |  |  |  | Line Marking |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-01-28: 0.00% Line Marking
|  | 4 | 1.1.2.2 |  |  |  | Check Floor Level |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Check Floor Level
|  | 4 | 1.1.2.3 |  |  |  | Check Line Marking |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Check Line Marking
|  | 4 | 1.1.2.4 |  |  |  | Drilling Anchor Hole |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Drilling Anchor Hole
|  | 4 | 1.1.2.5 |  |  |  | Move In |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00%; 2024-04-21: Move In
|  | 4 | 1.1.2.6 |  |  |  | Install Anchor & Nut |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Install Anchor & Nut
|  | 4 | 1.1.2.7 |  |  |  | Install Deck Post&Girder&Bracing |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Install Deck Post&Girder&Bracing
|  | 4 | 1.1.2.8 |  |  |  | Install Tower Stair |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Tower Stair
|  | 4 | 1.1.2.9 |  |  |  | Check Vertical(Deck Post&Tower Stair) |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Check Vertical(Deck Post&Tower Stair)
|  | 4 | 1.1.2.10 |  |  |  | Install Deck Frame&Hand Rail |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Deck Frame&Hand Rail
|  | 4 | 1.1.2.11 |  |  |  | Check Track Number |  | Lifter | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Check Track Number
|  | 4 | 1.1.2.12 |  |  |  | Install Lifter |  | Lifter | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Lifter
|  | 4 | 1.1.2.13 |  |  |  | Check Vertical |  | Lifter | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Check Vertical
|  | 4 | 1.1.2.14 |  |  |  | Setting Lifter Driving Accessories |  | Lifter | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Setting Lifter Driving Accessories
|  | 4 | 1.1.2.15 |  |  |  | Install Anchor |  | Lifter | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Anchor
|  | 4 | 1.1.2.16 |  |  |  | Install Anchor & Nut |  | deck(CV) | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Anchor & Nut
|  | 4 | 1.1.2.17 |  |  |  | Check Nut Level |  | deck(CV) | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Check Nut Level
|  | 4 | 1.1.2.18 |  |  |  | Install Deck Post&Girder(Floor 2) |  | deck(CV) | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Deck Post&Girder(Floor 2)
|  | 4 | 1.1.2.19 |  |  |  | Install Rail Base(Floor 2) |  | deck(CV) | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Rail Base(Floor 2)
|  | 4 | 1.1.2.20 |  |  |  | Check Rail Base Level |  | deck(CV) | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Check Rail Base Level
|  | 4 | 1.1.2.21 |  |  |  | Install Deck Frame(Floor 2) |  | deck(CV) | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Install Deck Frame(Floor 2)
|  | 4 | 1.1.2.22 |  |  |  | Check Track Number |  | C/V | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Check Track Number
|  | 4 | 1.1.2.23 |  |  |  | Install C/V(Floor 2) |  | C/V | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Install C/V(Floor 2)
|  | 4 | 1.1.2.24 |  |  |  | Install C/V(Floor 1) |  | C/V | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Install C/V(Floor 1)
|  | 4 | 1.1.2.25 |  |  |  | Check Center Line |  | C/V | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Check Center Line
|  | 4 | 1.1.2.26 |  |  |  | Check C/V Level |  | C/V | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Check C/V Level
|  | 4 | 1.1.2.27 |  |  |  | Install Anchor |  | C/V | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Install Anchor
|  | 4 | 1.1.2.28 |  |  |  | Install Fence |  | C/V | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Install Fence
|  | 4 | 1.1.2.29 |  |  |  | Install Under Rail & Top Rail |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Install Under Rail & Top Rail
|  | 4 | 1.1.2.30 |  |  |  | Check Leveling(U.R & T.R) |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Check Leveling(U.R & T.R)
|  | 4 | 1.1.2.31 |  |  |  | Check Center Line |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Check Center Line
|  | 4 | 1.1.2.32 |  |  |  | Install MSC |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Install MSC
|  | 4 | 1.1.2.33 |  |  |  | Install MSC Aceessories |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-24: 0.00% Install MSC Aceessories
|  | 4 | 1.1.2.34 |  |  |  | Install Water Tank |  | etc | [11 empty] | 1 |  |  |  |  | 2024-03-24: 0.00% Install Water Tank
|  | 4 | 1.1.2.35 |  |  |  | Grouting & Cleaning |  | etc | [11 empty] | 1 |  |  |  |  | 2024-01-14: 0.00% Grouting & Cleaning
| G | 3 | 1.1.3 |  |  | NT#1 |  |  | CA-NT#1 | [16 empty] | 2024-03-03: 0.00%; 2024-04-28: NT#1
|  | 4 | 1.1.3.1 |  |  |  | Line Marking |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Line Marking
|  | 4 | 1.1.3.2 |  |  |  | Check Floor Level |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Check Floor Level
|  | 4 | 1.1.3.3 |  |  |  | Check Line Marking |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Check Line Marking
|  | 4 | 1.1.3.4 |  |  |  | Drilling Anchor Hole |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Drilling Anchor Hole
|  | 4 | 1.1.3.5 |  |  |  | Move In |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00%; 2024-04-28: Move In
|  | 4 | 1.1.3.6 |  |  |  | Install Anchor & Nut |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Anchor & Nut
|  | 4 | 1.1.3.7 |  |  |  | Install Deck Post&Girder&Bracing |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Deck Post&Girder&Bracing
|  | 4 | 1.1.3.8 |  |  |  | Install Tower Stair |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Tower Stair
|  | 4 | 1.1.3.9 |  |  |  | Check Vertical(Deck Post&Tower Stair) |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Check Vertical(Deck Post&Tower Stair)
|  | 4 | 1.1.3.10 |  |  |  | Install Deck Frame&Hand Rail |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Deck Frame&Hand Rail
|  | 4 | 1.1.3.11 |  |  |  | Install Anchor |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Anchor
|  | 4 | 1.1.3.12 |  |  |  | Install Liner |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Liner
|  | 4 | 1.1.3.13 |  |  |  | Check Liner Leveling(Laser) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Check Liner Leveling(Laser)
|  | 4 | 1.1.3.14 |  |  |  | Install Base Plate |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Base Plate
|  | 4 | 1.1.3.15 |  |  |  | Erect Rack(2th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Erect Rack(2th)
|  | 4 | 1.1.3.16 |  |  |  | Install Lifter |  | Lifter | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Lifter
|  | 4 | 1.1.3.17 |  |  |  | Install Beam&Bracing(2th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Beam&Bracing(2th)
|  | 4 | 1.1.3.18 |  |  |  | Install Rack&Beam&Bracing(5th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Install Rack&Beam&Bracing(5th)
|  | 4 | 1.1.3.19 |  |  |  | Install Deck Frame&Hand Rail |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Install Deck Frame&Hand Rail
|  | 4 | 1.1.3.20 |  |  |  | Check Track No. |  | Home stand | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Check Track No.
|  | 4 | 1.1.3.21 |  |  |  | Install HP Home Stand & C/V |  | Home stand | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Install HP Home Stand & C/V
|  | 4 | 1.1.3.22 |  |  |  | Check home stand CV Level & Center line |  | Home stand | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Check home stand CV Level & Center line
|  | 4 | 1.1.3.23 |  |  |  | Pre-Assembly Rack(5~54Th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Pre-Assembly Rack(5~54Th)
|  | 4 | 1.1.3.24 |  |  |  | Install Rack&Beam&Bracing&Rail Base(10th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Rack&Beam&Bracing&Rail Base(10th)
|  | 4 | 1.1.3.25 |  |  |  | Check Vertical(1~10th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Check Vertical(1~10th)
|  | 4 | 1.1.3.26 |  |  |  | Install MSC Rail(1st rail) |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install MSC Rail(1st rail)
|  | 4 | 1.1.3.27 |  |  |  | Lifting MSC |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Lifting MSC
|  | 4 | 1.1.3.28 |  |  |  | Install Rack&Beam&Bracing&Rail Base(Every 10th, ~54th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Rack&Beam&Bracing&Rail Base(Every 10th, ~54th)
|  | 4 | 1.1.3.29 |  |  |  | Check Vertical(Every 10th, ~54th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Check Vertical(Every 10th, ~54th)
|  | 4 | 1.1.3.30 |  |  |  | Install MSC Rail(Every 10th, ~54th) |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Install MSC Rail(Every 10th, ~54th)
|  | 4 | 1.1.3.31 |  |  |  | Install Water Tank Assembly |  | Water tank | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Install Water Tank Assembly
|  | 4 | 1.1.3.32 |  |  |  | Install Rack&Beam&Bracing&Rail Base(~59th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Install Rack&Beam&Bracing&Rail Base(~59th)
|  | 4 | 1.1.3.33 |  |  |  | Install Deck Frame&Hand Rail |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-24: 0.00% Install Deck Frame&Hand Rail
|  | 4 | 1.1.3.34 |  |  |  | Check Track No. |  | Home stand(HP) | [11 empty] | 1 |  |  |  |  | 2024-03-31: 0.00% Check Track No.
|  | 4 | 1.1.3.35 |  |  |  | Install OP Home Stand |  | Home stand(HP) | [11 empty] | 1 |  |  |  |  | 2024-03-31: 0.00% Install OP Home Stand
|  | 4 | 1.1.3.36 |  |  |  | Check home stand CV Level & Center line |  | Home stand(HP) | [11 empty] | 1 |  |  |  |  | 2024-01-14: 0.00% Check home stand CV Level & Center line
|  | 4 | 1.1.3.37 |  |  |  | Install Rack(~60th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-31: 0.00% Install Rack(~60th)
|  | 4 | 1.1.3.38 |  |  |  | Install Lifter |  | Lifter | [11 empty] | 1 |  |  |  |  | 2024-03-31: 0.00% Install Lifter
|  | 4 | 1.1.3.39 |  |  |  | Install Tower Stair |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-04-07: 0.00% Install Tower Stair
|  | 4 | 1.1.3.40 |  |  |  | Install Rack(~61th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-04-07: 0.00% Install Rack(~61th)
|  | 4 | 1.1.3.41 |  |  |  | Install Top Cover, Rail Walk-Way, Top Maintenance Walk-Way |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-04-07: 0.00% Install Top Cover, Rail Walk-Way, Top Maintenance Walk-Way
|  | 4 | 1.1.3.42 |  |  |  | Install MSC Accessories |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-04-14: 0.00% Install MSC Accessories
|  | 4 | 1.1.3.43 |  |  |  | Check MSC rail straightness & rail/load arm level |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-04-14: 0.00% Check MSC rail straightness & rail/load arm level
|  | 4 | 1.1.3.44 |  |  |  | Install Smoke Detector |  | Smoke detector | [11 empty] | 1 |  |  |  |  | 2024-04-14: 0.00% Install Smoke Detector
|  | 4 | 1.1.3.45 |  |  |  | Install Anchor & Nut |  | Deck(OP) | [11 empty] | 1 |  |  |  |  | 2024-04-07: 0.00% Install Anchor & Nut
|  | 4 | 1.1.3.46 |  |  |  | Check Nut Level |  | Deck(OP) | [11 empty] | 1 |  |  |  |  | 2024-04-07: 0.00% Check Nut Level
|  | 4 | 1.1.3.47 |  |  |  | Install Deck Post&Girder&Bracing |  | Deck(OP) | [11 empty] | 1 |  |  |  |  | 2024-04-14: 0.00% Install Deck Post&Girder&Bracing
|  | 4 | 1.1.3.48 |  |  |  | Check Vertical(Deck Post) |  | Deck(OP) | [11 empty] | 1 |  |  |  |  | 2024-04-14: 0.00% Check Vertical(Deck Post)
|  | 4 | 1.1.3.49 |  |  |  | Install Deck Frame&Hand Rail |  | Deck(OP) | [11 empty] | 1 |  |  |  |  | 2024-04-14: 0.00% Install Deck Frame&Hand Rail
|  | 4 | 1.1.3.50 |  |  |  | Check Track No. |  | CV | [11 empty] | 1 |  |  |  |  | 2024-04-14: 0.00% Check Track No.
|  | 4 | 1.1.3.51 |  |  |  | Install C/V |  | CV | [11 empty] | 1 |  |  |  |  | 2024-04-14: 0.00% Install C/V
|  | 4 | 1.1.3.52 |  |  |  | Check C/V Level & Center line (TBD) |  | CV | [11 empty] | 1 |  |  |  |  | 2024-04-14: 0.00% Check C/V Level & Center line (TBD)
|  | 4 | 1.1.3.53 |  |  |  | install fence |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-04-21: 0.00% install fence
|  | 4 | 1.1.3.54 |  |  |  | Grouting & Cleaning |  | Deck | [11 empty] | 1 |  |  |  |  | 2024-04-21: 0.00% Grouting & Cleaning
| G | 3 | 1.1.4 |  |  | NT#2,3(4,5,6Lane) |  |  | CA-NT#2,3 | [16 empty] | 2024-02-04: 0.00%; 2024-04-07: NT#2,3(4,5,6Lane)
|  | 4 | 1.1.4.1 |  |  |  | Line Marking |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Line Marking
|  | 4 | 1.1.4.2 |  |  |  | Check Floor Level |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Check Floor Level
|  | 4 | 1.1.4.3 |  |  |  | Check Line Marking |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Check Line Marking
|  | 4 | 1.1.4.4 |  |  |  | Drilling Anchor Hole |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Drilling Anchor Hole
|  | 4 | 1.1.4.5 |  |  |  | Move In |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00%; 2024-04-07: Move In
|  | 4 | 1.1.4.6 |  |  |  | Install Anchor & Nut |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Anchor & Nut
|  | 4 | 1.1.4.7 |  |  |  | Install Deck Post&Girder&Bracing |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Deck Post&Girder&Bracing
|  | 4 | 1.1.4.8 |  |  |  | Check Vertical(Deck Post&Tower Stair) |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Check Vertical(Deck Post&Tower Stair)
|  | 4 | 1.1.4.9 |  |  |  | Install Deck Frame&Hand Rail |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Deck Frame&Hand Rail
|  | 4 | 1.1.4.10 |  |  |  | Install Anchor |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Anchor
|  | 4 | 1.1.4.11 |  |  |  | Install Liner |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Liner
|  | 4 | 1.1.4.12 |  |  |  | Check Liner Leveling(Laser) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Check Liner Leveling(Laser)
|  | 4 | 1.1.4.13 |  |  |  | Install Base Plate |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Base Plate
|  | 4 | 1.1.4.14 |  |  |  | Erect Rack(2th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Erect Rack(2th)
|  | 4 | 1.1.4.15 |  |  |  | Install Lifter |  | Lifter | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Lifter
|  | 4 | 1.1.4.16 |  |  |  | Install Beam&Bracing(2th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Beam&Bracing(2th)
|  | 4 | 1.1.4.17 |  |  |  | Install Rack&Beam&Bracing(5th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Rack&Beam&Bracing(5th)
|  | 4 | 1.1.4.18 |  |  |  | Install Deck Frame&Hand Rail |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Install Deck Frame&Hand Rail
|  | 4 | 1.1.4.19 |  |  |  | Check Track No. |  | Home stand | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Check Track No.
|  | 4 | 1.1.4.20 |  |  |  | Install HP Home Stand & C/V |  | Home stand | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Install HP Home Stand & C/V
|  | 4 | 1.1.4.21 |  |  |  | Check home stand CV Level & Center line |  | Home stand | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Check home stand CV Level & Center line
|  | 4 | 1.1.4.22 |  |  |  | Pre-Assembly Rack(5~69h) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Pre-Assembly Rack(5~69h)
|  | 4 | 1.1.4.23 |  |  |  | Install Rack&Beam&Bracing&Rail Base(10th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Rack&Beam&Bracing&Rail Base(10th)
|  | 4 | 1.1.4.24 |  |  |  | Check Vertical(1~10th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Check Vertical(1~10th)
|  | 4 | 1.1.4.25 |  |  |  | Install MSC Rail(1st rail) |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install MSC Rail(1st rail)
|  | 4 | 1.1.4.26 |  |  |  | Lifting MSC |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Lifting MSC
|  | 4 | 1.1.4.27 |  |  |  | Install Rack&Beam&Bracing&Rail Base(Every 10th, ~69th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Rack&Beam&Bracing&Rail Base(Every 10th, ~69th)
|  | 4 | 1.1.4.28 |  |  |  | Check Vertical(Every 10th, ~69th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Check Vertical(Every 10th, ~69th)
|  | 4 | 1.1.4.29 |  |  |  | Install MSC Rail(Every 10th, ~69th) |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Install MSC Rail(Every 10th, ~69th)
|  | 4 | 1.1.4.30 |  |  |  | Install Water Tank Assembly |  | Water tank | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Install Water Tank Assembly
|  | 4 | 1.1.4.31 |  |  |  | Install Rack&Beam&Bracing&Rail Base(~75th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Install Rack&Beam&Bracing&Rail Base(~75th)
|  | 4 | 1.1.4.32 |  |  |  | Install Deck Frame&Hand Rail |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-24: 0.00% Install Deck Frame&Hand Rail
|  | 4 | 1.1.4.33 |  |  |  | Install Tower Stair |  | deck(OP side) | [11 empty] | 1 |  |  |  |  | 2024-03-24: 0.00% Install Tower Stair
|  | 4 | 1.1.4.34 |  |  |  | Install Top Cover, Rail Walk-Way, Top Maintenance Walk-Way |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-24: 0.00% Install Top Cover, Rail Walk-Way, Top Maintenance Walk-Way
|  | 4 | 1.1.4.35 |  |  |  | Install MSC Accessories |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-31: 0.00% Install MSC Accessories
|  | 4 | 1.1.4.36 |  |  |  | Check MSC rail straightness & rail/load arm level |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-31: 0.00% Check MSC rail straightness & rail/load arm level
|  | 4 | 1.1.4.37 |  |  |  | Install Smoke Detector |  | Smoke detector | [11 empty] | 1 |  |  |  |  | 2024-03-31: 0.00% Install Smoke Detector
|  | 4 | 1.1.4.38 |  |  |  | install fence |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-04-07: 0.00% install fence
|  | 4 | 1.1.4.39 |  |  |  | Grouting & Cleaning |  | Deck | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Grouting & Cleaning
| G | 3 | 1.1.5 |  |  | NT#2,3(1,2,3Lane) |  |  | CA-NT#2,3 | [16 empty] | 2024-02-04: 0.00%; 2024-04-07: NT#2,3(1,2,3Lane)
|  | 4 | 1.1.5.1 |  |  |  | Line Marking |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Line Marking
|  | 4 | 1.1.5.2 |  |  |  | Check Floor Level |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Check Floor Level
|  | 4 | 1.1.5.3 |  |  |  | Check Line Marking |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Check Line Marking
|  | 4 | 1.1.5.4 |  |  |  | Drilling Anchor Hole |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Drilling Anchor Hole
|  | 4 | 1.1.5.5 |  |  |  | Move In |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00%; 2024-04-07: Move In
|  | 4 | 1.1.5.6 |  |  |  | Install Anchor & Nut |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Anchor & Nut
|  | 4 | 1.1.5.7 |  |  |  | Install Deck Post&Girder&Bracing |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Deck Post&Girder&Bracing
|  | 4 | 1.1.5.8 |  |  |  | Check Vertical(Deck Post&Tower Stair) |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Check Vertical(Deck Post&Tower Stair)
|  | 4 | 1.1.5.9 |  |  |  | Install Deck Frame&Hand Rail |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Deck Frame&Hand Rail
|  | 4 | 1.1.5.10 |  |  |  | Install Anchor |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Anchor
|  | 4 | 1.1.5.11 |  |  |  | Install Liner |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Liner
|  | 4 | 1.1.5.12 |  |  |  | Check Liner Leveling(Laser) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Check Liner Leveling(Laser)
|  | 4 | 1.1.5.13 |  |  |  | Install Base Plate |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Base Plate
|  | 4 | 1.1.5.14 |  |  |  | Erect Rack(2th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Erect Rack(2th)
|  | 4 | 1.1.5.15 |  |  |  | Install Lifter |  | Lifter | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Lifter
|  | 4 | 1.1.5.16 |  |  |  | Install Beam&Bracing(2th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Beam&Bracing(2th)
|  | 4 | 1.1.5.17 |  |  |  | Install Rack&Beam&Bracing(5th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Rack&Beam&Bracing(5th)
|  | 4 | 1.1.5.18 |  |  |  | Install Deck Frame&Hand Rail |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Install Deck Frame&Hand Rail
|  | 4 | 1.1.5.19 |  |  |  | Check Track No. |  | Home stand | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Check Track No.
|  | 4 | 1.1.5.20 |  |  |  | Install HP Home Stand & C/V |  | Home stand | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Install HP Home Stand & C/V
|  | 4 | 1.1.5.21 |  |  |  | Check home stand CV Level & Center line |  | Home stand | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Check home stand CV Level & Center line
|  | 4 | 1.1.5.22 |  |  |  | Pre-Assembly Rack(5~69h) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Pre-Assembly Rack(5~69h)
|  | 4 | 1.1.5.23 |  |  |  | Install Rack&Beam&Bracing&Rail Base(10th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Rack&Beam&Bracing&Rail Base(10th)
|  | 4 | 1.1.5.24 |  |  |  | Check Vertical(1~10th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Check Vertical(1~10th)
|  | 4 | 1.1.5.25 |  |  |  | Install MSC Rail(1st rail) |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install MSC Rail(1st rail)
|  | 4 | 1.1.5.26 |  |  |  | Lifting MSC |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Lifting MSC
|  | 4 | 1.1.5.27 |  |  |  | Install Rack&Beam&Bracing&Rail Base(Every 10th, ~69th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Rack&Beam&Bracing&Rail Base(Every 10th, ~69th)
|  | 4 | 1.1.5.28 |  |  |  | Check Vertical(Every 10th, ~69th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Check Vertical(Every 10th, ~69th)
|  | 4 | 1.1.5.29 |  |  |  | Install MSC Rail(Every 10th, ~69th) |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Install MSC Rail(Every 10th, ~69th)
|  | 4 | 1.1.5.30 |  |  |  | Install Water Tank Assembly |  | Water tank | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Install Water Tank Assembly
|  | 4 | 1.1.5.31 |  |  |  | Install Rack&Beam&Bracing&Rail Base(~75th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Install Rack&Beam&Bracing&Rail Base(~75th)
|  | 4 | 1.1.5.32 |  |  |  | Install Deck Frame&Hand Rail |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-24: 0.00% Install Deck Frame&Hand Rail
|  | 4 | 1.1.5.33 |  |  |  | Install Top Cover, Rail Walk-Way, Top Maintenance Walk-Way |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-24: 0.00% Install Top Cover, Rail Walk-Way, Top Maintenance Walk-Way
|  | 4 | 1.1.5.34 |  |  |  | Install MSC Accessories |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-24: 0.00% Install MSC Accessories
|  | 4 | 1.1.5.35 |  |  |  | Check MSC rail straightness & rail/load arm level |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-31: 0.00% Check MSC rail straightness & rail/load arm level
|  | 4 | 1.1.5.36 |  |  |  | Install Smoke Detector |  | Smoke detector | [11 empty] | 1 |  |  |  |  | 2024-03-31: 0.00% Install Smoke Detector
|  | 4 | 1.1.5.37 |  |  |  | install fence |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-31: 0.00% install fence
|  | 4 | 1.1.5.38 |  |  |  | Grouting & Cleaning |  | Deck | [11 empty] | 1 |  |  |  |  | 2024-04-07: 0.00% Grouting & Cleaning
| G | 3 | 1.1.6 |  |  | Empty Tray(South) |  |  | CA-Empty | [16 empty] | 2024-03-03: 0.00%; 2024-03-31: Empty Tray(South)
|  | 4 | 1.1.6.1 |  |  |  | Line Marking |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Line Marking
|  | 4 | 1.1.6.2 |  |  |  | Check Floor Level |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Check Floor Level
|  | 4 | 1.1.6.3 |  |  |  | Check Line Marking |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Check Line Marking
|  | 4 | 1.1.6.4 |  |  |  | Drilling Anchor Hole |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Drilling Anchor Hole
|  | 4 | 1.1.6.5 |  |  |  | Move In |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00%; 2024-03-31: Move In
|  | 4 | 1.1.6.6 |  |  |  | Install Anchor |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Anchor
|  | 4 | 1.1.6.7 |  |  |  | Install Liner |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Liner
|  | 4 | 1.1.6.8 |  |  |  | Check Liner Leveling(Laser) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Check Liner Leveling(Laser)
|  | 4 | 1.1.6.9 |  |  |  | Pre-Assembly Rack(2~32h) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Pre-Assembly Rack(2~32h)
|  | 4 | 1.1.6.10 |  |  |  | Install Base Plate |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Base Plate
|  | 4 | 1.1.6.11 |  |  |  | Install Rack&Beam&Bracing&Rail Base(10th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Rack&Beam&Bracing&Rail Base(10th)
|  | 4 | 1.1.6.12 |  |  |  | Check Vertical(1~10th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Check Vertical(1~10th)
|  | 4 | 1.1.6.13 |  |  |  | Install MSC Rail(1st rail) |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install MSC Rail(1st rail)
|  | 4 | 1.1.6.14 |  |  |  | Install MSC |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install MSC
|  | 4 | 1.1.6.15 |  |  |  | Install Rack&Beam&Bracing&Rail Base(Every 10th, ~35th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Rack&Beam&Bracing&Rail Base(Every 10th, ~35th)
|  | 4 | 1.1.6.16 |  |  |  | Check Vertical(Every 10th, ~35th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Check Vertical(Every 10th, ~35th)
|  | 4 | 1.1.6.17 |  |  |  | Install MSC Rail(Every 10th, ~35th) |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Install MSC Rail(Every 10th, ~35th)
|  | 4 | 1.1.6.18 |  |  |  | Install MSC Accessories |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Install MSC Accessories
|  | 4 | 1.1.6.19 |  |  |  | Check MSC rail straightness & rail/load arm level |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Check MSC rail straightness & rail/load arm level
|  | 4 | 1.1.6.20 |  |  |  | install fence |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-24: 0.00% install fence
| G | 3 | 1.1.7 |  |  | Empty Tray(North) |  |  | CA-Empty | [16 empty] | 2024-02-25: 0.00%; 2024-04-21: Empty Tray(North)
|  | 4 | 1.1.7.1 |  |  |  | Line Marking |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Line Marking
|  | 4 | 1.1.7.2 |  |  |  | Check Floor Level |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Check Floor Level
|  | 4 | 1.1.7.3 |  |  |  | Check Line Marking |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Check Line Marking
|  | 4 | 1.1.7.4 |  |  |  | Drilling Anchor Hole |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Drilling Anchor Hole
|  | 4 | 1.1.7.5 |  |  |  | Move In |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00%; 2024-03-31: Move In
|  | 4 | 1.1.7.6 |  |  |  | Install Anchor |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Anchor
|  | 4 | 1.1.7.7 |  |  |  | Install Liner |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Liner
|  | 4 | 1.1.7.8 |  |  |  | Check Liner Leveling(Laser) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Check Liner Leveling(Laser)
|  | 4 | 1.1.7.9 |  |  |  | Pre-Assembly Rack(2~32h) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Pre-Assembly Rack(2~32h)
|  | 4 | 1.1.7.10 |  |  |  | Install Base Plate |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Install Base Plate
|  | 4 | 1.1.7.11 |  |  |  | Install Rack&Beam&Bracing&Rail Base(10th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Install Rack&Beam&Bracing&Rail Base(10th)
|  | 4 | 1.1.7.12 |  |  |  | Check Vertical(1~10th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Check Vertical(1~10th)
|  | 4 | 1.1.7.13 |  |  |  | Install MSC Rail(1st rail) |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Install MSC Rail(1st rail)
|  | 4 | 1.1.7.14 |  |  |  | Install MSC |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Install MSC
|  | 4 | 1.1.7.15 |  |  |  | Install Rack&Beam&Bracing&Rail Base(Every 10th, ~35th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Install Rack&Beam&Bracing&Rail Base(Every 10th, ~35th)
|  | 4 | 1.1.7.16 |  |  |  | Check Vertical(Every 10th, ~35th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Check Vertical(Every 10th, ~35th)
|  | 4 | 1.1.7.17 |  |  |  | Install MSC Rail(Every 10th, ~35th) |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Install MSC Rail(Every 10th, ~35th)
|  | 4 | 1.1.7.18 |  |  |  | Install MSC Accessories |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-31: 0.00% Install MSC Accessories
|  | 4 | 1.1.7.19 |  |  |  | Check MSC rail straightness & rail/load arm level |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-04-07: 0.00% Check MSC rail straightness & rail/load arm level
|  | 4 | 1.1.7.20 |  |  |  | install fence |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-04-14: 0.00% install fence
| G | 3 | 1.1.8 |  |  | HT#1 |  |  | CA-HT#1 | [16 empty] | 2024-02-04: 0.00%; 2024-04-07: HT#1
|  | 4 | 1.1.8.1 |  |  |  | Line Marking |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Line Marking
|  | 4 | 1.1.8.2 |  |  |  | Check Floor Level |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Check Floor Level
|  | 4 | 1.1.8.3 |  |  |  | Check Line Marking |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Check Line Marking
|  | 4 | 1.1.8.4 |  |  |  | Drilling Anchor Hole |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Drilling Anchor Hole
|  | 4 | 1.1.8.5 |  |  |  | Move In |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00%; 2024-04-07: Move In
|  | 4 | 1.1.8.6 |  |  |  | Install Anchor & Nut |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Anchor & Nut
|  | 4 | 1.1.8.7 |  |  |  | Install Deck Post&Girder&Bracing |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Deck Post&Girder&Bracing
|  | 4 | 1.1.8.8 |  |  |  | Check Vertical(Deck Post&Tower Stair) |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Check Vertical(Deck Post&Tower Stair)
|  | 4 | 1.1.8.9 |  |  |  | Install Deck Frame&Hand Rail |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Deck Frame&Hand Rail
|  | 4 | 1.1.8.10 |  |  |  | Install Anchor |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Anchor
|  | 4 | 1.1.8.11 |  |  |  | Install Liner |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Liner
|  | 4 | 1.1.8.12 |  |  |  | Check Liner Leveling(Laser) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Check Liner Leveling(Laser)
|  | 4 | 1.1.8.13 |  |  |  | Install Base Plate |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Base Plate
|  | 4 | 1.1.8.14 |  |  |  | Erect Rack(2th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Erect Rack(2th)
|  | 4 | 1.1.8.15 |  |  |  | Install Lifter |  | Lifter | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Lifter
|  | 4 | 1.1.8.16 |  |  |  | Install Beam&Bracing(2th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Beam&Bracing(2th)
|  | 4 | 1.1.8.17 |  |  |  | Install Rack&Beam&Bracing(5th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Rack&Beam&Bracing(5th)
|  | 4 | 1.1.8.18 |  |  |  | Install Deck Frame&Hand Rail |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Install Deck Frame&Hand Rail
|  | 4 | 1.1.8.19 |  |  |  | Check Track No. |  | Home stand | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Check Track No.
|  | 4 | 1.1.8.20 |  |  |  | Install HP Home Stand & C/V |  | Home stand | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Install HP Home Stand & C/V
|  | 4 | 1.1.8.21 |  |  |  | Check home stand CV Level & Center line |  | Home stand | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Check home stand CV Level & Center line
|  | 4 | 1.1.8.22 |  |  |  | Pre-Assembly Rack(5~58h) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Pre-Assembly Rack(5~58h)
|  | 4 | 1.1.8.23 |  |  |  | Install Rack&Beam&Bracing&Rail Base(10th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Rack&Beam&Bracing&Rail Base(10th)
|  | 4 | 1.1.8.24 |  |  |  | Check Vertical(1~10th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Check Vertical(1~10th)
|  | 4 | 1.1.8.25 |  |  |  | Install MSC Rail(1st rail) |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install MSC Rail(1st rail)
|  | 4 | 1.1.8.26 |  |  |  | Lifting MSC |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Lifting MSC
|  | 4 | 1.1.8.27 |  |  |  | Install Rack&Beam&Bracing&Rail Base(Every 10th, ~59th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Rack&Beam&Bracing&Rail Base(Every 10th, ~59th)
|  | 4 | 1.1.8.28 |  |  |  | Check Vertical(Every 10th, ~59th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Check Vertical(Every 10th, ~59th)
|  | 4 | 1.1.8.29 |  |  |  | Install MSC Rail(Every 10th, ~59th) |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Install MSC Rail(Every 10th, ~59th)
|  | 4 | 1.1.8.30 |  |  |  | Install Water Tank Assembly |  | Water tank | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Install Water Tank Assembly
|  | 4 | 1.1.8.31 |  |  |  | Install Rack&Beam&Bracing&Rail Base(~62th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Install Rack&Beam&Bracing&Rail Base(~62th)
|  | 4 | 1.1.8.32 |  |  |  | Install Deck Frame&Hand Rail |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-24: 0.00% Install Deck Frame&Hand Rail
|  | 4 | 1.1.8.33 |  |  |  | Install Top Cover, Rail Walk-Way, Top Maintenance Walk-Way |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-24: 0.00% Install Top Cover, Rail Walk-Way, Top Maintenance Walk-Way
|  | 4 | 1.1.8.34 |  |  |  | Install MSC Accessories |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-24: 0.00% Install MSC Accessories
|  | 4 | 1.1.8.35 |  |  |  | Check MSC rail straightness & rail/load arm level |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-31: 0.00% Check MSC rail straightness & rail/load arm level
|  | 4 | 1.1.8.36 |  |  |  | Install Tower Stair |  | deck(OP side) | [11 empty] | 1 |  |  |  |  | 2024-03-31: 0.00% Install Tower Stair
|  | 4 | 1.1.8.37 |  |  |  | Install Smoke Detector |  | Smoke detector | [11 empty] | 1 |  |  |  |  | 2024-03-31: 0.00% Install Smoke Detector
|  | 4 | 1.1.8.38 |  |  |  | install fence |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-04-07: 0.00% install fence
|  | 4 | 1.1.8.39 |  |  |  | Grouting & Cleaning |  | Deck | [11 empty] | 1 |  |  |  |  | 2024-04-07: 0.00% Grouting & Cleaning
| G | 3 | 1.1.9 |  |  | HT#2 |  |  | CA-HT#2 | [16 empty] | 2024-02-04: 0.00%; 2024-04-07: HT#2
|  | 4 | 1.1.9.1 |  |  |  | Line Marking |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Line Marking
|  | 4 | 1.1.9.2 |  |  |  | Check Floor Level |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Check Floor Level
|  | 4 | 1.1.9.3 |  |  |  | Check Line Marking |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Check Line Marking
|  | 4 | 1.1.9.4 |  |  |  | Drilling Anchor Hole |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Drilling Anchor Hole
|  | 4 | 1.1.9.5 |  |  |  | Move In |  | Pre-Work | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00%; 2024-04-07: Move In
|  | 4 | 1.1.9.6 |  |  |  | Install Anchor & Nut |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Anchor & Nut
|  | 4 | 1.1.9.7 |  |  |  | Install Deck Post&Girder&Bracing |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Deck Post&Girder&Bracing
|  | 4 | 1.1.9.8 |  |  |  | Check Vertical(Deck Post&Tower Stair) |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Check Vertical(Deck Post&Tower Stair)
|  | 4 | 1.1.9.9 |  |  |  | Install Deck Frame&Hand Rail |  | deck(High) | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Deck Frame&Hand Rail
|  | 4 | 1.1.9.10 |  |  |  | Install Anchor |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Anchor
|  | 4 | 1.1.9.11 |  |  |  | Install Liner |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Liner
|  | 4 | 1.1.9.12 |  |  |  | Check Liner Leveling(Laser) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Check Liner Leveling(Laser)
|  | 4 | 1.1.9.13 |  |  |  | Install Base Plate |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Base Plate
|  | 4 | 1.1.9.14 |  |  |  | Erect Rack(2th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Erect Rack(2th)
|  | 4 | 1.1.9.15 |  |  |  | Install Lifter |  | Lifter | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Lifter
|  | 4 | 1.1.9.16 |  |  |  | Install Beam&Bracing(2th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Beam&Bracing(2th)
|  | 4 | 1.1.9.17 |  |  |  | Install Rack&Beam&Bracing(5th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Rack&Beam&Bracing(5th)
|  | 4 | 1.1.9.18 |  |  |  | Install Deck Frame&Hand Rail |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Install Deck Frame&Hand Rail
|  | 4 | 1.1.9.19 |  |  |  | Check Track No. |  | Home stand | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Check Track No.
|  | 4 | 1.1.9.20 |  |  |  | Install HP Home Stand & C/V |  | Home stand | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Install HP Home Stand & C/V
|  | 4 | 1.1.9.21 |  |  |  | Check home stand CV Level & Center line |  | Home stand | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Check home stand CV Level & Center line
|  | 4 | 1.1.9.22 |  |  |  | Pre-Assembly Rack(5~58h) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Pre-Assembly Rack(5~58h)
|  | 4 | 1.1.9.23 |  |  |  | Install Rack&Beam&Bracing&Rail Base(10th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Rack&Beam&Bracing&Rail Base(10th)
|  | 4 | 1.1.9.24 |  |  |  | Check Vertical(1~10th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Check Vertical(1~10th)
|  | 4 | 1.1.9.25 |  |  |  | Install MSC Rail(1st rail) |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install MSC Rail(1st rail)
|  | 4 | 1.1.9.26 |  |  |  | Lifting MSC |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Lifting MSC
|  | 4 | 1.1.9.27 |  |  |  | Install Rack&Beam&Bracing&Rail Base(Every 10th, ~59th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Rack&Beam&Bracing&Rail Base(Every 10th, ~59th)
|  | 4 | 1.1.9.28 |  |  |  | Check Vertical(Every 10th, ~59th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Check Vertical(Every 10th, ~59th)
|  | 4 | 1.1.9.29 |  |  |  | Install MSC Rail(Every 10th, ~59th) |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Install MSC Rail(Every 10th, ~59th)
|  | 4 | 1.1.9.30 |  |  |  | Install Water Tank Assembly |  | Water tank | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Install Water Tank Assembly
|  | 4 | 1.1.9.31 |  |  |  | Install Rack&Beam&Bracing&Rail Base(~62th) |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Install Rack&Beam&Bracing&Rail Base(~62th)
|  | 4 | 1.1.9.32 |  |  |  | Install Deck Frame&Hand Rail |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-24: 0.00% Install Deck Frame&Hand Rail
|  | 4 | 1.1.9.33 |  |  |  | Install Top Cover, Rail Walk-Way, Top Maintenance Walk-Way |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-03-24: 0.00% Install Top Cover, Rail Walk-Way, Top Maintenance Walk-Way
|  | 4 | 1.1.9.34 |  |  |  | Install MSC Accessories |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-24: 0.00% Install MSC Accessories
|  | 4 | 1.1.9.35 |  |  |  | Check MSC rail straightness & rail/load arm level |  | MSC | [11 empty] | 1 |  |  |  |  | 2024-03-31: 0.00% Check MSC rail straightness & rail/load arm level
|  | 4 | 1.1.9.36 |  |  |  | Install Tower Stair |  | deck(OP side) | [11 empty] | 1 |  |  |  |  | 2024-03-31: 0.00% Install Tower Stair
|  | 4 | 1.1.9.37 |  |  |  | Install Smoke Detector |  | Smoke detector | [11 empty] | 1 |  |  |  |  | 2024-03-31: 0.00% Install Smoke Detector
|  | 4 | 1.1.9.38 |  |  |  | install fence |  | Rack | [11 empty] | 1 |  |  |  |  | 2024-04-07: 0.00% install fence
|  | 4 | 1.1.9.39 |  |  |  | Grouting & Cleaning |  | Deck | [11 empty] | 1 |  |  |  |  | 2024-04-07: 0.00% Grouting & Cleaning
| G | 3 | 1.1.10 |  |  | Assembly |  |  | CA-Assembly | [16 empty] | 2024-03-10: 0.00% Assembly
|  | 4 | 1.1.10.1 |  |  |  | Line Marking |  | CV | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Line Marking
|  | 4 | 1.1.10.2 |  |  |  | Check Line Marking |  | CV | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Check Line Marking
|  | 4 | 1.1.10.3 |  |  |  | Drilling Anchor Hole |  | CV | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Drilling Anchor Hole
|  | 4 | 1.1.10.4 |  |  |  | Move In |  | CV | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Move In
|  | 4 | 1.1.10.5 |  |  |  | Install Anchor |  | Deck | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Install Anchor
|  | 4 | 1.1.10.6 |  |  |  | Install Deck Post |  | Deck | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Deck Post
|  | 4 | 1.1.10.7 |  |  |  | Install Deck Frame&Hand Rail |  | Deck | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Install Deck Frame&Hand Rail
|  | 4 | 1.1.10.8 |  |  |  | Install Lifter |  | Lifter | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Install Lifter
|  | 4 | 1.1.10.9 |  |  |  | Check Deck Level |  | Deck | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Check Deck Level
|  | 4 | 1.1.10.10 |  |  |  | Check Track NO. |  | CV | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Check Track NO.
|  | 4 | 1.1.10.11 |  |  |  | Pre-assembly C/V |  | CV | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Pre-assembly C/V
|  | 4 | 1.1.10.12 |  |  |  | Install C/V |  | CV | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Install C/V
|  | 4 | 1.1.10.13 |  |  |  | Check C/V Level Center Line |  | CV | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Check C/V Level Center Line
|  | 4 | 1.1.10.14 |  |  |  | Install Stair |  | CV | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Install Stair
| G | 3 | 1.1.11 |  |  | Interconnect(Recollect) |  |  | CA-Interconnect | [16 empty] | 2024-02-04: 0.00%; 2024-03-10: Interconnect(Recollect)
|  | 4 | 1.1.11.1 |  |  |  | Line Marking |  | CV | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Line Marking
|  | 4 | 1.1.11.2 |  |  |  | Check Line Marking |  | CV | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Check Line Marking
|  | 4 | 1.1.11.3 |  |  |  | Drilling Anchor Hole |  | CV | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Drilling Anchor Hole
|  | 4 | 1.1.11.4 |  |  |  | Move In |  | CV | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Move In
|  | 4 | 1.1.11.5 |  |  |  | Floor Lifter Erection & Lifting |  | Lifter | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Floor Lifter Erection & Lifting
|  | 4 | 1.1.11.6 |  |  |  | Floor Lifter mast Alignment |  | Lifter | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Floor Lifter mast Alignment
|  | 4 | 1.1.11.7 |  |  |  | Floor Lifter Anchoring |  | Lifter | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Floor Lifter Anchoring
|  | 4 | 1.1.11.8 |  |  |  | Setting Lifter Inside |  | Lifter | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Setting Lifter Inside
|  | 4 | 1.1.11.9 |  |  |  | Install Deck(Sq 1-4, 1-5, after EMPT east rack/MSC install) |  | Deck | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Deck(Sq 1-4, 1-5, after EMPT east rack/MSC install)
|  | 4 | 1.1.11.10 |  |  |  | Deck Lifter lifting & Alignment |  | Lifter | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Deck Lifter lifting & Alignment
|  | 4 | 1.1.11.11 |  |  |  | Deck CV Center Line Marking |  | CV | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Deck CV Center Line Marking
|  | 4 | 1.1.11.12 |  |  |  | Incoming PassBox & Install |  | Deck | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Incoming PassBox & Install
|  | 4 | 1.1.11.13 |  |  |  | Install Horizontal Shutter |  | Deck | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Install Horizontal Shutter
|  | 4 | 1.1.11.14 |  |  |  | Check Track Number |  | CV | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Check Track Number
|  | 4 | 1.1.11.15 |  |  |  | Install CV |  | CV | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Install CV
|  | 4 | 1.1.11.16 |  |  |  | Check C/V Level Center Line |  | CV | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Check C/V Level Center Line
|  | 4 | 1.1.11.17 |  |  |  | C/V Anchor |  | CV | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% C/V Anchor
|  | 4 | 1.1.11.18 |  |  |  | Install Stair |  | CV | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Install Stair
| G | 3 | 1.1.12 |  |  | Interconnect(Aging) |  |  | CA-Interconnect | [16 empty] | 2024-02-04: 0.00%; 2024-03-10: Interconnect(Aging)
|  | 4 | 1.1.12.1 |  |  |  | Line Marking |  | CV | [11 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Line Marking
|  | 4 | 1.1.12.2 |  |  |  | Check Line Marking |  | CV | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Check Line Marking
|  | 4 | 1.1.12.3 |  |  |  | Drilling Anchor Hole |  | CV | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Drilling Anchor Hole
|  | 4 | 1.1.12.4 |  |  |  | Move In |  | CV | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Move In
|  | 4 | 1.1.12.5 |  |  |  | Install Deck |  | Deck | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Deck
|  | 4 | 1.1.12.6 |  |  |  | Deck Lifter lifting & Alignment |  | Lifter | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Deck Lifter lifting & Alignment
|  | 4 | 1.1.12.7 |  |  |  | Deck CV Center Line Marking |  | CV | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Deck CV Center Line Marking
|  | 4 | 1.1.12.8 |  |  |  | Incoming PassBox & Install |  | Deck | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Incoming PassBox & Install
|  | 4 | 1.1.12.9 |  |  |  | Check Track Number |  | CV | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Check Track Number
|  | 4 | 1.1.12.10 |  |  |  | Install CV |  | CV | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Install CV
|  | 4 | 1.1.12.11 |  |  |  | Check C/V Level Center Line |  | CV | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Check C/V Level Center Line
|  | 4 | 1.1.12.12 |  |  |  | C/V Anchor |  | CV | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% C/V Anchor
|  | 4 | 1.1.12.13 |  |  |  | Install Stair |  | CV | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Install Stair
| G | 3 | 1.1.13 |  |  | 1F Conveyor |  |  | CA-1F Conveyor | [16 empty] | 2024-02-11: 0.00%; 2024-08-04: 1F Conveyor
|  | 4 | 1.1.13.1 |  |  |  | Line Marking |  | CV | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Line Marking
|  | 4 | 1.1.13.2 |  |  |  | Check Line Marking |  | CV | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Check Line Marking
|  | 4 | 1.1.13.3 |  |  |  | Move In |  | CV | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00%; 2024-03-24: Move In
|  | 4 | 1.1.13.4 |  |  |  | Check Track Number |  | CV | [11 empty] | 1 |  |  |  |  | 2024-03-24: 0.00% Check Track Number
|  | 4 | 1.1.13.5 |  |  |  | Install CV (folding CV) |  | CV | [11 empty] | 1 |  |  |  |  | 2024-03-31: 0.00%; 2024-05-05: Install CV (folding CV)
|  | 4 | 1.1.13.6 |  |  |  | Check C/V Level Center Line |  | CV | [11 empty] | 1 |  |  |  |  | 2024-05-05: 0.00%; 2024-06-02: Check C/V Level Center Line
|  | 4 | 1.1.13.7 |  |  |  | C/V Anchor |  | CV | [11 empty] | 1 |  |  |  |  | 2024-06-02: 0.00% C/V Anchor
|  | 4 | 1.1.13.8 |  |  |  | Install Stair |  | CV | [11 empty] | 1 |  |  |  |  | 2024-06-09: 0.00%; 2024-07-14: Install Stair
|  | 4 | 1.1.13.9 |  |  |  | Install Deck(jump) |  | Deck | [11 empty] | 1 |  |  |  |  | 2024-07-14: 0.00% Install Deck(jump)
|  | 4 | 1.1.13.10 |  |  |  | Lifter Erection & Alignment |  | Lifter | [11 empty] | 1 |  |  |  |  | 2024-07-14: 0.00% Lifter Erection & Alignment
|  | 4 | 1.1.13.11 |  |  |  | Check Deck Level |  | Deck | [11 empty] | 1 |  |  |  |  | 2024-07-14: 0.00% Check Deck Level
|  | 4 | 1.1.13.12 |  |  |  | Install CV (IR OCV, NG sorter) |  | CV | [11 empty] | 1 |  |  |  |  | 2024-07-14: 0.00% Install CV (IR OCV, NG sorter)
|  | 4 | 1.1.13.13 |  |  |  | Check C/V Level Center Line |  | CV | [11 empty] | 1 |  |  |  |  | 2024-07-21: 0.00% Check C/V Level Center Line
|  | 4 | 1.1.13.14 |  |  |  | C/V Anchor |  | CV | [11 empty] | 1 |  |  |  |  | 2024-07-28: 0.00% C/V Anchor
|  | 4 | 1.1.13.15 |  |  |  | Install Stair |  | CV | [11 empty] | 1 |  |  |  |  | 2024-07-28: 0.00% Install Stair
| G | 3 | 1.1.14 |  |  | 2F Conveyor DGS front ※Front |  |  | CA-DGS front Conveyor | [16 empty] | 2024-02-11: 0.00%; 2024-03-17: 2F Conveyor DGS front ※Front
|  | 4 | 1.1.14.1 |  |  |  | Line Marking |  | CV | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Line Marking
ㅑ |  | 4 | 1.1.14.2 |  |  |  | Check Line Marking |  | CV | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Check Line Marking
|  | 4 | 1.1.14.3 |  |  |  | Move In |  | CV | [11 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Move In
|  | 4 | 1.1.14.4 |  |  |  | Install Anchor |  | Deck | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Anchor
|  | 4 | 1.1.14.5 |  |  |  | Install Deck Post |  | Deck | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Deck Post
|  | 4 | 1.1.14.6 |  |  |  | Install Deck Frame&Hand Rail |  | Deck | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Deck Frame&Hand Rail
|  | 4 | 1.1.14.7 |  |  |  | Install Lifter |  | Lifter | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install Lifter
|  | 4 | 1.1.14.8 |  |  |  | Check Deck Level |  | Deck | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Check Deck Level
|  | 4 | 1.1.14.9 |  |  |  | Check Track NO. |  | CV | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Check Track NO.
|  | 4 | 1.1.14.10 |  |  |  | Install C/V (DGS front) |  | CV | [11 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Install C/V (DGS front)
|  | 4 | 1.1.14.11 |  |  |  | Check C/V Level Center Line |  | CV | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Check C/V Level Center Line
|  | 4 | 1.1.14.12 |  |  |  | Install Stair |  | CV | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Install Stair
| G | 3 | 1.1.15 |  |  | 2F Conveyor DGS back ※Back |  |  | CA-DGS back Conveyor | [16 empty] | 2024-02-25: 0.00%; 2024-05-19: 2F Conveyor DGS back ※Back
|  | 4 | 1.1.15.1 |  |  |  | Line Marking |  | CV | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Line Marking
|  | 4 | 1.1.15.2 |  |  |  | Check Line Marking |  | CV | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Check Line Marking
|  | 4 | 1.1.15.3 |  |  |  | Move In |  | CV | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Move In
|  | 4 | 1.1.15.4 |  |  |  | Check Track Number |  | CV | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Check Track Number
|  | 4 | 1.1.15.5 |  |  |  | Install CV (DGS back CV) |  | CV | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Install CV (DGS back CV)
|  | 4 | 1.1.15.6 |  |  |  | Check C/V Level Center Line |  | CV | [11 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Check C/V Level Center Line
|  | 4 | 1.1.15.7 |  |  |  | C/V Anchor |  | CV | [11 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% C/V Anchor
|  | 4 | 1.1.15.8 |  |  |  | Install Stair |  | CV | [11 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Install Stair
|  | 4 | 1.1.15.9 |  |  |  | Install Deck(jump) |  | Deck | [11 empty] | 1 |  |  |  |  | 2024-03-24: 0.00% Install Deck(jump)
|  | 4 | 1.1.15.10 |  |  |  | Lifter Erection & Alignment |  | Lifter | [11 empty] | 1 |  |  |  |  | 2024-03-31: 0.00% Lifter Erection & Alignment
|  | 4 | 1.1.15.11 |  |  |  | Check Deck Level |  | Deck | [11 empty] | 1 |  |  |  |  | 2024-03-31: 0.00% Check Deck Level
|  | 4 | 1.1.15.12 |  |  |  | Install CV (IR OCV, NG sorter) |  | CV | [11 empty] | 1 |  |  |  |  | 2024-03-31: 0.00% Install CV (IR OCV, NG sorter)
|  | 4 | 1.1.15.13 |  |  |  | Check C/V Level Center Line |  | CV | [11 empty] | 1 |  |  |  |  | 2024-03-31: 0.00% Check C/V Level Center Line
|  | 4 | 1.1.15.14 |  |  |  | C/V Anchor |  | CV | [11 empty] | 1 |  |  |  |  | 2024-03-31: 0.00% C/V Anchor
|  | 4 | 1.1.15.15 |  |  |  | Install Stair |  | CV | [11 empty] | 1 |  |  |  |  | 2024-03-31: 0.00%; 2024-05-19: Install Stair
| G | 1 | 2 | Hook UP |  |  |  |  | Hook UP | [16 empty] | 2023-12-03: 0.00%; 2024-05-05: Hook UP
| G | 2 | 2.1 |  | Cathode |  |  |  | Cathode | [16 empty] | 2023-12-03: 0.00%; 2024-05-05: Cathode
| G | 3 | 2.1.1 |  |  | PPC Room |  |  | CA-PPC | [16 empty] | 2024-02-18: 0.00% PPC Room
|  | 4 | 2.1.1.1 |  |  |  | PPC Room-1, Deck | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% PPC Room-1, Deck
|  | 4 | 2.1.1.2 |  |  |  | PPC Room-1, TRANSFER+C/V | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% PPC Room-1, TRANSFER+C/V
|  | 4 | 2.1.1.3 |  |  |  | PPC Room-1, LIFTER | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% PPC Room-1, LIFTER
|  | 4 | 2.1.1.4 |  |  |  | PPC Room-1, MSC(3대) | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% PPC Room-1, MSC(3대)
|  | 4 | 2.1.1.5 |  |  |  | PPC Room-1, MSC(5대) | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% PPC Room-1, MSC(5대)
|  | 4 | 2.1.1.6 |  |  |  | Panel Alignment and fixation | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Panel Alignment and fixation
|  | 4 | 2.1.1.7 |  |  |  | Door S/W SOP LCP positioning in alignment | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Door S/W SOP LCP positioning in alignment
|  | 4 | 2.1.1.8 |  |  |  | Install Duct | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Duct
|  | 4 | 2.1.1.9 |  |  |  | Installation Lifter cable | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Installation Lifter cable
|  | 4 | 2.1.1.10 |  |  |  | Installation Power moller cable | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Installation Power moller cable
|  | 4 | 2.1.1.11 |  |  |  | Installation Lifter Light Curtain cable | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Installation Lifter Light Curtain cable
|  | 4 | 2.1.1.12 |  |  |  | installation DP Mg 24VDC Cable | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% installation DP Mg 24VDC Cable
|  | 4 | 2.1.1.13 |  |  |  | Installation Servo Cable | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Installation Servo Cable
|  | 4 | 2.1.1.14 |  |  |  | Cable installation work related to fire suppression tank | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Cable installation work related to fire suppression tank
|  | 4 | 2.1.1.15 |  |  |  | Door S/W SOP LCP cable Installation | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Door S/W SOP LCP cable Installation
|  | 4 | 2.1.1.16 |  |  |  | Installation Panel Inside Cable | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Installation Panel Inside Cable
|  | 4 | 2.1.1.17 |  |  |  | Installation LED LAMP | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Installation LED LAMP
|  | 4 | 2.1.1.18 |  |  |  | Installation Collector Arm | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Installation Collector Arm
|  | 4 | 2.1.1.19 |  |  |  | Attach Tape(Driving BCR) | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Attach Tape(Driving BCR)
|  | 4 | 2.1.1.20 |  |  |  | Installation Motor Cable | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Installation Motor Cable
| G | 3 | 2.1.2 |  |  | Charger Room |  |  | CA-FCH | [16 empty] | 2024-02-18: 0.00%; 2024-05-05: Charger Room
|  | 4 | 2.1.2.1 |  |  |  | Panel Alignment and fixation | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00%; 2024-05-05: Panel Alignment and fixation
|  | 4 | 2.1.2.2 |  |  |  | Door S/W SOP LCP positioning in alignment | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00%; 2024-05-05: Door S/W SOP LCP positioning in alignment
|  | 4 | 2.1.2.3 |  |  |  | Install Duct | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00%; 2024-05-05: Install Duct
|  | 4 | 2.1.2.4 |  |  |  | Installation Lifter cable | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00%; 2024-05-05: Installation Lifter cable
|  | 4 | 2.1.2.5 |  |  |  | Installation Power moller cable | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00%; 2024-05-05: Installation Power moller cable
|  | 4 | 2.1.2.6 |  |  |  | Installation Lifter Light Curtain cable | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00%; 2024-05-05: Installation Lifter Light Curtain cable
|  | 4 | 2.1.2.7 |  |  |  | Turn Table 24VDC Cable installation | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00%; 2024-05-05: Turn Table 24VDC Cable installation
|  | 4 | 2.1.2.8 |  |  |  | Cable installation work related to fire suppression tank | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00%; 2024-05-05: Cable installation work related to fire suppression tank
|  | 4 | 2.1.2.9 |  |  |  | Door S/W SOP LCP cable Installation | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00%; 2024-05-05: Door S/W SOP LCP cable Installation
|  | 4 | 2.1.2.10 |  |  |  | Installation Panel Inside Cable | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00%; 2024-05-05: Installation Panel Inside Cable
|  | 4 | 2.1.2.11 |  |  |  | Installation LED LAMP | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00%; 2024-05-05: Installation LED LAMP
|  | 4 | 2.1.2.12 |  |  |  | Installation Collector Arm | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00%; 2024-05-05: Installation Collector Arm
|  | 4 | 2.1.2.13 |  |  |  | Attach Tape(Driving BCR) | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00%; 2024-05-05: Attach Tape(Driving BCR)
|  | 4 | 2.1.2.14 |  |  |  | Installation Motor Cable | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00%; 2024-05-05: Installation Motor Cable
| G | 3 | 2.1.3 |  |  | NT#1 |  |  | CA-NT#1 | [16 empty] | 2024-01-28: 0.00%; 2024-02-18: NT#1
|  | 4 | 2.1.3.1 |  |  |  | Panel Alignment and fixation | [13 empty] | 1 |  |  |  |  | 2024-01-28: 0.00% Panel Alignment and fixation
|  | 4 | 2.1.3.2 |  |  |  | Door S/W SOP LCP positioning in alignment | [13 empty] | 1 |  |  |  |  | 2024-01-28: 0.00% Door S/W SOP LCP positioning in alignment
|  | 4 | 2.1.3.3 |  |  |  | Install Duct | [13 empty] | 1 |  |  |  |  | 2024-01-28: 0.00% Install Duct
|  | 4 | 2.1.3.4 |  |  |  | Installation Lifter cable | [13 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Installation Lifter cable
|  | 4 | 2.1.3.5 |  |  |  | Installation Power moller cable | [13 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Installation Power moller cable
|  | 4 | 2.1.3.6 |  |  |  | Installation Lifter Light Curtain cable | [13 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Installation Lifter Light Curtain cable
|  | 4 | 2.1.3.7 |  |  |  | Cable installation work related to fire suppression tank | [13 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Cable installation work related to fire suppression tank
|  | 4 | 2.1.3.8 |  |  |  | Door S/W SOP LCP cable Installation | [13 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Door S/W SOP LCP cable Installation
|  | 4 | 2.1.3.9 |  |  |  | Installation Panel Inside Cable | [13 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Installation Panel Inside Cable
|  | 4 | 2.1.3.10 |  |  |  | Installation LED LAMP | [13 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Installation LED LAMP
|  | 4 | 2.1.3.11 |  |  |  | Installation Collector Arm | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Installation Collector Arm
|  | 4 | 2.1.3.12 |  |  |  | Attach Tape(Driving BCR) | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Attach Tape(Driving BCR)
|  | 4 | 2.1.3.13 |  |  |  | Installation Motor Cable | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Installation Motor Cable
| G | 3 | 2.1.4 |  |  | NT#2,3 |  |  | CA-NT#2,3 | [16 empty] | 2024-02-18: 0.00% NT#2,3
|  | 4 | 2.1.4.1 |  |  |  | Panel Alignment and fixation | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Panel Alignment and fixation
|  | 4 | 2.1.4.2 |  |  |  | Door S/W SOP LCP positioning in alignment | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Door S/W SOP LCP positioning in alignment
|  | 4 | 2.1.4.3 |  |  |  | Install Duct | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Install Duct
|  | 4 | 2.1.4.4 |  |  |  | Installation Lifter cable | [13 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Installation Lifter cable
|  | 4 | 2.1.4.5 |  |  |  | Installation Power moller cable | [13 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Installation Power moller cable
|  | 4 | 2.1.4.6 |  |  |  | Installation Lifter Light Curtain cable | [13 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Installation Lifter Light Curtain cable
|  | 4 | 2.1.4.7 |  |  |  | Cable installation work related to fire suppression tank | [13 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Cable installation work related to fire suppression tank
|  | 4 | 2.1.4.8 |  |  |  | Door S/W SOP LCP cable Installation | [13 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Door S/W SOP LCP cable Installation
|  | 4 | 2.1.4.9 |  |  |  | Installation Panel Inside Cable | [13 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Installation Panel Inside Cable
|  | 4 | 2.1.4.10 |  |  |  | Installation LED LAMP | [13 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Installation LED LAMP
|  | 4 | 2.1.4.11 |  |  |  | Installation Collector Arm | [13 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Installation Collector Arm
|  | 4 | 2.1.4.12 |  |  |  | Attach Tape(Driving BCR) | [13 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Attach Tape(Driving BCR)
|  | 4 | 2.1.4.13 |  |  |  | Installation Motor Cable | [13 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Installation Motor Cable
| G | 3 | 2.1.5 |  |  | Empty Tray |  |  | CA-Empty | [16 empty] | 2024-01-28: 0.00%; 2024-02-18: Empty Tray
|  | 4 | 2.1.5.1 |  |  |  | Panel Alignment and fixation | [13 empty] | 1 |  |  |  |  | 2024-01-28: 0.00% Panel Alignment and fixation
|  | 4 | 2.1.5.2 |  |  |  | Door S/W SOP LCP positioning in alignment | [13 empty] | 1 |  |  |  |  | 2024-01-28: 0.00% Door S/W SOP LCP positioning in alignment
|  | 4 | 2.1.5.3 |  |  |  | Install Duct | [13 empty] | 1 |  |  |  |  | 2024-01-28: 0.00% Install Duct
|  | 4 | 2.1.5.4 |  |  |  | Installation Lifter cable | [13 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Installation Lifter cable
|  | 4 | 2.1.5.5 |  |  |  | Installation Power moller cable | [13 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Installation Power moller cable
|  | 4 | 2.1.5.6 |  |  |  | Installation Lifter Light Curtain cable | [13 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Installation Lifter Light Curtain cable
|  | 4 | 2.1.5.7 |  |  |  | Door S/W SOP LCP cable Installation | [13 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Door S/W SOP LCP cable Installation
|  | 4 | 2.1.5.8 |  |  |  | Installation Panel Inside Cable | [13 empty] | 1 |  |  |  |  | 2024-02-04: 0.00% Installation Panel Inside Cable
|  | 4 | 2.1.5.9 |  |  |  | Installation Collector Arm | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Installation Collector Arm
|  | 4 | 2.1.5.10 |  |  |  | Attach Tape(Driving BCR) | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Attach Tape(Driving BCR)
|  | 4 | 2.1.5.11 |  |  |  | Installation Motor Cable | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Installation Motor Cable
| G | 3 | 2.1.6 |  |  | HT#1 |  |  | CA-HT#1 | [16 empty] | 2024-02-11: 0.00% HT#1
|  | 4 | 2.1.6.1 |  |  |  | Panel Alignment and fixation | [13 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Panel Alignment and fixation
|  | 4 | 2.1.6.2 |  |  |  | Door S/W SOP LCP positioning in alignment | [13 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Door S/W SOP LCP positioning in alignment
|  | 4 | 2.1.6.3 |  |  |  | Install Duct | [13 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Duct
|  | 4 | 2.1.6.4 |  |  |  | Installation Lifter cable | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Installation Lifter cable
|  | 4 | 2.1.6.5 |  |  |  | Installation Power moller cable | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Installation Power moller cable
|  | 4 | 2.1.6.6 |  |  |  | Installation Lifter Light Curtain cable | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Installation Lifter Light Curtain cable
|  | 4 | 2.1.6.7 |  |  |  | Cable installation work related to fire suppression tank | [13 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Cable installation work related to fire suppression tank
|  | 4 | 2.1.6.8 |  |  |  | Door S/W SOP LCP cable Installation | [13 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Door S/W SOP LCP cable Installation
|  | 4 | 2.1.6.9 |  |  |  | Installation Panel Inside Cable | [13 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Installation Panel Inside Cable
|  | 4 | 2.1.6.10 |  |  |  | Installation LED LAMP | [13 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Installation LED LAMP
|  | 4 | 2.1.6.11 |  |  |  | Installation Collector Arm | [13 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Installation Collector Arm
|  | 4 | 2.1.6.12 |  |  |  | Attach Tape(Driving BCR) | [13 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Attach Tape(Driving BCR)
|  | 4 | 2.1.6.13 |  |  |  | Installation Motor Cable | [13 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Installation Motor Cable
| G | 3 | 2.1.7 |  |  | HT#2 |  |  | CA-HT#2 | [16 empty] | 2024-02-11: 0.00% HT#2
|  | 4 | 2.1.7.1 |  |  |  | Panel Alignment and fixation | [13 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Panel Alignment and fixation
|  | 4 | 2.1.7.2 |  |  |  | Door S/W SOP LCP positioning in alignment | [13 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Door S/W SOP LCP positioning in alignment
|  | 4 | 2.1.7.3 |  |  |  | Install Duct | [13 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Duct
|  | 4 | 2.1.7.4 |  |  |  | Installation Lifter cable | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Installation Lifter cable
|  | 4 | 2.1.7.5 |  |  |  | Installation Power moller cable | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Installation Power moller cable
|  | 4 | 2.1.7.6 |  |  |  | Installation Lifter Light Curtain cable |  | CA-HT#2-1 | [11 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Installation Lifter Light Curtain cable
|  | 4 | 2.1.7.7 |  |  |  | Cable installation work related to fire suppression tank | [13 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Cable installation work related to fire suppression tank
|  | 4 | 2.1.7.8 |  |  |  | Door S/W SOP LCP cable Installation | [13 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Door S/W SOP LCP cable Installation
|  | 4 | 2.1.7.9 |  |  |  | Installation Panel Inside Cable | [13 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Installation Panel Inside Cable
|  | 4 | 2.1.7.10 |  |  |  | Installation LED LAMP | [13 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Installation LED LAMP
|  | 4 | 2.1.7.11 |  |  |  | Installation Collector Arm | [13 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Installation Collector Arm
|  | 4 | 2.1.7.12 |  |  |  | Attach Tape(Driving BCR) | [13 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Attach Tape(Driving BCR)
|  | 4 | 2.1.7.13 |  |  |  | Installation Motor Cable | [13 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Installation Motor Cable
| G | 3 | 2.1.8 |  |  | Assembly |  |  | CA-Assembly | [16 empty] | 2023-12-03: 0.00% Assembly
|  | 4 | 2.1.8.1 |  |  |  | Panel Alignment and fixation | [13 empty] | 1 |  |  |  |  | 2023-12-03: 0.00% Panel Alignment and fixation
|  | 4 | 2.1.8.2 |  |  |  | Door S/W SOP LCP positioning in alignment | [13 empty] | 1 |  |  |  |  | 2023-12-03: 0.00% Door S/W SOP LCP positioning in alignment
|  | 4 | 2.1.8.3 |  |  |  | Install Duct | [13 empty] | 1 |  |  |  |  | 2023-12-03: 0.00% Install Duct
|  | 4 | 2.1.8.4 |  |  |  | Installation Lifter cable | [13 empty] | 1 |  |  |  |  | 2023-12-10: 0.00% Installation Lifter cable
|  | 4 | 2.1.8.5 |  |  |  | Installation Power moller cable | [13 empty] | 1 |  |  |  |  | 2023-12-10: 0.00% Installation Power moller cable
|  | 4 | 2.1.8.6 |  |  |  | Installation Lifter Light Curtain cable | [13 empty] | 1 |  |  |  |  | 2023-12-10: 0.00% Installation Lifter Light Curtain cable
|  | 4 | 2.1.8.7 |  |  |  | Installation DP MG Cable | [13 empty] | 1 |  |  |  |  | 2023-12-17: 0.00% Installation DP MG Cable
|  | 4 | 2.1.8.8 |  |  |  | Installation Panel Inside Cable | [13 empty] | 1 |  |  |  |  | 2023-12-17: 0.00% Installation Panel Inside Cable
|  | 4 | 2.1.8.9 |  |  |  | Installation LED LAMP | [13 empty] | 1 |  |  |  |  | 2023-12-24: 0.00% Installation LED LAMP
| G | 3 | 2.1.9 |  |  | Interconnect |  |  | CA-Interconnect | [16 empty] | 2024-03-10: 0.00% Interconnect
|  | 4 | 2.1.9.1 |  |  |  | Panel Alignment and fixation | [13 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Panel Alignment and fixation
|  | 4 | 2.1.9.2 |  |  |  | Door S/W SOP LCP positioning in alignment | [13 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Door S/W SOP LCP positioning in alignment
|  | 4 | 2.1.9.3 |  |  |  | Install Duct | [13 empty] | 1 |  |  |  |  | 2024-03-10: 0.00% Install Duct
|  | 4 | 2.1.9.4 |  |  |  | Installation Lifter cable | [13 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Installation Lifter cable
|  | 4 | 2.1.9.5 |  |  |  | Installation Power moller cable | [13 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Installation Power moller cable
|  | 4 | 2.1.9.6 |  |  |  | Installation Lifter Light Curtain cable | [13 empty] | 1 |  |  |  |  | 2024-03-17: 0.00% Installation Lifter Light Curtain cable
|  | 4 | 2.1.9.7 |  |  |  | Installation DP MG TT Cable | [13 empty] | 1 |  |  |  |  | 2024-03-24: 0.00% Installation DP MG TT Cable
|  | 4 | 2.1.9.8 |  |  |  | Installation Panel Inside Cable | [13 empty] | 1 |  |  |  |  | 2024-03-24: 0.00% Installation Panel Inside Cable
|  | 4 | 2.1.9.9 |  |  |  | Installation LED LAMP | [13 empty] | 1 |  |  |  |  | 2024-03-31: 0.00% Installation LED LAMP
| G | 3 | 2.1.10 |  |  | 1F Conveyor |  |  | CA-1F Conveyor | [16 empty] | 2023-12-24: 0.00%; 2024-01-14: 1F Conveyor
|  | 4 | 2.1.10.1 |  |  |  | Panel Alignment and fixation | [13 empty] | 1 |  |  |  |  | 2023-12-24: 0.00% Panel Alignment and fixation
|  | 4 | 2.1.10.2 |  |  |  | Door S/W SOP LCP positioning in alignment | [13 empty] | 1 |  |  |  |  | 2023-12-24: 0.00% Door S/W SOP LCP positioning in alignment
|  | 4 | 2.1.10.3 |  |  |  | Install Duct | [13 empty] | 1 |  |  |  |  | 2023-12-24: 0.00% Install Duct
|  | 4 | 2.1.10.4 |  |  |  | Installation Lifter cable | [13 empty] | 1 |  |  |  |  | 2023-12-31: 0.00% Installation Lifter cable
|  | 4 | 2.1.10.5 |  |  |  | Installation Power moller cable | [13 empty] | 1 |  |  |  |  | 2023-12-31: 0.00% Installation Power moller cable
|  | 4 | 2.1.10.6 |  |  |  | Installation Lifter Light Curtain cable | [13 empty] | 1 |  |  |  |  | 2023-12-31: 0.00% Installation Lifter Light Curtain cable
|  | 4 | 2.1.10.7 |  |  |  | Installation DP MG TT Cable | [13 empty] | 1 |  |  |  |  | 2023-12-31: 0.00% Installation DP MG TT Cable
|  | 4 | 2.1.10.8 |  |  |  | Installation Panel Inside Cable | [13 empty] | 1 |  |  |  |  | 2024-01-07: 0.00% Installation Panel Inside Cable
| G | 3 | 2.1.11 |  |  | 2F Conveyor DGS front ※Front |  |  | CA-DGS front Conveyor | [16 empty] | 2023-12-03: 0.00% 2F Conveyor DGS front ※Front
|  | 4 | 2.1.11.1 |  |  |  | Panel Alignment and fixation | [13 empty] | 1 |  |  |  |  | 2023-12-03: 0.00% Panel Alignment and fixation
|  | 4 | 2.1.11.2 |  |  |  | Door S/W SOP LCP positioning in alignment | [13 empty] | 1 |  |  |  |  | 2023-12-03: 0.00% Door S/W SOP LCP positioning in alignment
|  | 4 | 2.1.11.3 |  |  |  | Install Duct | [13 empty] | 1 |  |  |  |  | 2023-12-03: 0.00% Install Duct
|  | 4 | 2.1.11.4 |  |  |  | Installation Lifter cable | [13 empty] | 1 |  |  |  |  | 2023-12-10: 0.00% Installation Lifter cable
|  | 4 | 2.1.11.5 |  |  |  | Installation Power moller cable | [13 empty] | 1 |  |  |  |  | 2023-12-10: 0.00% Installation Power moller cable
|  | 4 | 2.1.11.6 |  |  |  | Installation Lifter Light Curtain cable | [13 empty] | 1 |  |  |  |  | 2023-12-10: 0.00% Installation Lifter Light Curtain cable
|  | 4 | 2.1.11.7 |  |  |  | Installation DP MG TT Cable | [13 empty] | 1 |  |  |  |  | 2023-12-17: 0.00% Installation DP MG TT Cable
|  | 4 | 2.1.11.8 |  |  |  | Installation Panel Inside Cable | [13 empty] | 1 |  |  |  |  | 2023-12-17: 0.00% Installation Panel Inside Cable
|  | 4 | 2.1.11.9 |  |  |  | Installation LED LAMP | [13 empty] | 1 |  |  |  |  | 2023-12-24: 0.00% Installation LED LAMP
| G | 3 | 2.1.12 |  |  | 2F Conveyor DGS back ※Back |  |  | CA-DGS back Conveyor | [16 empty] | 2024-02-11: 0.00%; 2024-03-03: 2F Conveyor DGS back ※Back
|  | 4 | 2.1.12.1 |  |  |  | Panel Alignment and fixation | [13 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Panel Alignment and fixation
|  | 4 | 2.1.12.2 |  |  |  | Door S/W SOP LCP positioning in alignment | [13 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Door S/W SOP LCP positioning in alignment
|  | 4 | 2.1.12.3 |  |  |  | Install Duct | [13 empty] | 1 |  |  |  |  | 2024-02-11: 0.00% Install Duct
|  | 4 | 2.1.12.4 |  |  |  | Installation Lifter cable | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Installation Lifter cable
|  | 4 | 2.1.12.5 |  |  |  | Installation Power moller cable | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Installation Power moller cable
|  | 4 | 2.1.12.6 |  |  |  | Installation Lifter Light Curtain cable | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Installation Lifter Light Curtain cable
|  | 4 | 2.1.12.7 |  |  |  | Installation DP MG TT Cable | [13 empty] | 1 |  |  |  |  | 2024-02-18: 0.00% Installation DP MG TT Cable
|  | 4 | 2.1.12.8 |  |  |  | Installation Panel Inside Cable | [13 empty] | 1 |  |  |  |  | 2024-02-25: 0.00% Installation Panel Inside Cable
|  | 4 | 2.1.12.9 |  |  |  | Installation LED LAMP | [13 empty] | 1 |  |  |  |  | 2024-03-03: 0.00% Installation LED LAMP
| G | 1 | 6 | 연동Test | [5 empty] | 2024-04-01 | 2024-09-30 |  | 170 | 0 | 183 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2024-03-31: 0.00%; 2024-09-29: 연동Test 4/1-9/30
| G | 2 | 6.1 |  | BOSK TN |  |  |  |  | 2024-04-01 | 2024-09-30 |  | 170 | 0 | 183 | 0 |  |  | 0 | 0 |  |  |  | 0% | 0% | 2024-03-31: 0.00%; 2024-09-29: BOSK TN 4/1-9/30
|  | 3 | 6.1.1 |  |  | SW 현장설치 |  |  |  | 2024-04-01 | 2024-05-31 | 60 | 61 | 0 | 61 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2024-03-31: 0.00%; 2024-05-26: SW 현장설치 4/1-5/31
|  | 3 | 6.1.2 |  |  | Interface Test |  |  |  | 2024-06-15 | 2024-07-15 | 30 | 31 | 0 | 31 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2024-06-09: 0.00%; 2024-07-14: Interface Test 6/15-7/15
|  | 3 | 6.1.3 |  |  | 연동 Test 및 사용자운영교육 |  |  |  | 2024-07-15 | 2024-09-30 | 77 | 78 | 0 | 78 | 0 |  |  |  | 0 | 1 |  |  | 0% | 0% | 2024-07-14: 0.00%; 2024-09-29: 연동 Test 및 사용자운영교육 7/15-9/30

## 5. 위험성평가표(최초, 정기, 수시)
공정명: BOSK TN1 Aging & Convyeyor System |  |  | 위험성평가표 (조사표/개선계획/실행) | [9 empty] | 평가일시 |  |  | 작성 | 검토 | 승인
세부공정 | [12 empty] | 2024. 08. 19. |  |  | 이찬희 | 이창노 | 이창노
No. | 공정분류 | 작업내용 | 사용 기계기구 | 사용 화학물질 | 유해·위험요인파악 (조사표) |  |  | 현재 안전보건 조치 | 현재위험성 |  |  | 위험성 감소대책 (계획/실행) | 개선 후 위험성 |  |  | 개선 예정일 | 담당자 | 개선 완료일
[5 empty] | 분류 번호 | 유해위험요인(분류표참조) | 위험상황 및 잠재적 결과 |  | 가능성 (빈도) | 중대성 (강도) | 위험성 |  | 가능성 (빈도) | 중대성 (강도) | 위험성
1 | 자재반입(입고) | 설비 반입 | 대차 구획 정리 펜스 | 없음 | 1.1 | 1.1 협착위험 부분(감김, 끼임) | 설비 이동중 협착 위험 | 안전감시단 배치 | 2 | 2 | 4 | 이동동선 확보 및 운반대차운용 | 1 | 1 | 1 | 8/19 | 이찬희
2 | 설비(장비)설치_기구 | 작업구역 설정 | 대차 구획 정리 펜스 | 없음 | 1.1 | 1.1 협착위험 부분(감김, 끼임) | C/V, Rail,Rack, 설비 설치 중 협착 위험 | 안전감시단 배치 | 1 | 2 | 2 | 4면 작업구획 설정 및 인원통제 | 1 | 2 | 2 | 8/19 | 이찬희
5 | 설비(장비)설치_기구 | CV,MSC,RACK 양중 작업 | 지게차 크레인 | 없음 | 1.3 | 1.3 기계·설비의 낙하, 비래, 전복, 붕괴, 전도위험 부분 | 양중물 전도, 낙하 위험 | 작업 규정 준수 | 1 | 3 | 3 | 작업 반경 내 외부 작업 인원 접근 금지 | 1 | 3 | 3 | 8/19 | 이찬희
3 | 설비(장비)설치_기구 | CV,MSC,RACK 레벨 작업 | 수공구 드릴 레벨기 | 없음 | 1.1 | 1.1 협착위험 부분(감김, 끼임) | Rail,Rack, 설비 설치 중 협착 위험 | 안전보호구 착용 | 2 | 2 | 4 | 작업 반경 내 외부 작업 인원 접근 금지 | 2 | 2 | 4 | 8/19 | 이찬희
4 | 설비(장비)설치_기구 | CV,MSC,RACK 직진도 작업 | 수공구 | 없음 | 1.1 | 1.1 협착위험 부분(감김, 끼임) | Rail,Rack, 설비 설치 중 협착 위험 | 안전보호구 착용 | 2 | 2 | 4 | 작업규정 강화, 정기 휴식시간 확보 | 1 | 2 | 2 | 8/19 | 이찬희
6 | 설비(장비)설치_전장 | CV,MSC Duct 배관 작업 | 수공구 | 없음 | 1.1 | 1.1 협착위험 부분(감김, 끼임) | 덕트 고정 작업시 끼임 | 안전보호구 착용 | 2 | 2 | 4 | 작업규정 강화 및 2인1조 작업 실시 | 1 | 1 | 1 | 8/19 | 이찬희
7 | 설비(장비)설치_전장 | CV,MSC 배선 작업 | 수공구 | 없음 | 2.1 | 2.1 감전(안전전압 초과) | 판넬, 센서 접촉시 감전 위험 | 안전감시단 배치 | 1 | 2 | 2 | 안전보호구 착용 철저 접지 확인, 작업 중 전원공급 금지 | 1 | 2 | 2 | 8/19 | 이찬희
8 | 설비(장비)설치_전장 | I/O Check | 수공구 테스터기 | 없음 | 2.1 | 2.1 감전(안전전압 초과) | 판넬, 센서 접촉시 감전 위험 | 작업 규정 준수 | 2 | 2 | 4 | 전기 작업시 활선경보기 착용 및 접지상태 확인 후 작업 실시 | 1 | 2 | 2 | 8/19 | 이찬희
9 | 시운전 | 연결물류 Teaching | 수공구 드릴 | 없음 | 1.1 | 1.1 협착위험 부분(감김, 끼임) | CV-상대 연결물류 간 협착 위험 | 작업 규정 준수 | 2 | 3 | 6 | 안전보호구 착용 철저 3인1조작업 작업규정 강화, 정기 휴식시간 확보 | 1 | 2 | 2 | 8/19 | 이찬희
10 | 시운전 | 시운전 테스트 | 수공구 | 없음 | 1.4 | 1.4 충돌위험 부분 | CV 상부 화물 이동중 충돌 위험 | 작업 규정 준수 | 2 | 3 | 6 | 작업 반경 내 외부 작업 인원 접근 금지 | 1 | 2 | 2 | 8/19 | 이찬희
추가 사항 |  |  | 참여 근로자 | [9 empty] | 성 명 : ( 서 명 )
|  |  | 협력사 관리자 | [9 empty] | 성 명 : ( 서 명 )
|  |  | 안전관리자 | [9 empty] | 성 명 : ( 서 명 )
|  |  | 관리책임자 | [9 empty] | 성 명 : ( 서 명 )
비 고 란

## 6. 참조자료(유해위험요인, 위험성추정)
유해위험요인 분류표
【안전 분야】 | [7 empty] | 【보건 분야】
대구분 | 분류번호 | 유해위험요인 | [5 empty] | 대구분 | 분류번호 | 유해위험요인 | 분류번호 | 유해위험요인
기계적 | 1.1 | 협착위험 부분(감김, 끼임) | [5 empty] | 화학적 (물질) | 5.1 | 가스 | 5.7 | 방사선
| 1.2 | 위험한 표면(절단, 베임, 긁힘) | [6 empty] | 5.2 | 증기 | 5.8 | 화재/폭발 위험
| 1.3 | 기계·설비의 낙하, 비래, 전복, 붕괴, 전도위험 부분 | [6 empty] | 5.3 | 에어로졸·흄 | 5.9 | 복사열/폭발과압
| 1.4 | 충돌위험 부분 | [6 empty] | 5.4 | 액체·미스트
| 1.5 | 넘어짐(미끄러짐, 걸림, 헛디딤) | [6 empty] | 5.5 | 고체(분진/파우더)
| 1.6 | 추락위험 부분(개구부 등) | [6 empty] | 5.6 | 반응성 물질
전기적 | 2.1 | 감전(안전전압 초과) | [5 empty] | 물리적 | 6.1 | 기후/고온/저온(한랭) | 6.5 | 저압 또는 고압상태
| 2.2 | 아크 | [6 empty] | 6.2 | 조도(채광/조명) | 6.6 | 방사선
| 2.3 | 정전기 | [6 empty] | 6.3 | 소음 | 6.7 | 전자파
작업특성 | 3.1 | 초음파·초저주파음 | [6 empty] | 6.4 | 진동
| 3.2 | 근로자 실수(휴먼에러) | [5 empty] | 인간 공학적 | 7.1 | 중량물 취급작업 | 7.4 | 과도한 힘
| 3.3 | 질식위험·산소결핍 | [6 empty] | 7.2 | 반복작업 | 7.5 | 접촉스트레스
| 3.4 | 작업(조작) 도구 | [6 empty] | 7.3 | 불안정한 작업자세
작업환경 | 4.1 | 공간 및 이동통로 | [5 empty] | 생물학적 | 8.1 | 병원성 미생물, 바이러스에 의한 감염 | 8.4 | 동물
| 4.2 | 주변 근로자
| 4.3 | 작업시간 | [6 empty] | 8.2 | 유전자 변형물질(GMO) | 8.5 | 식물
| 4.4 | 조직 안전문화 | [6 empty] | 8.3 | 알러지 및 미생물
가능성(빈도) 산정 | [10 empty] | 중대성(강도) 산정
가능성(빈도) |  | 내 용 | [8 empty] | 중대성(강도) |  | 내 용
5 | 매우높음 | ■ 피해가 발생할 가능성이 매우 높음 - 해당 안전대책이 되어 있지 않고, 표시·표지가 없으며 안전수칙·작업표준 등도 없음 | [8 empty] | 4 | 중대재해 | 사망 또는 영구적 근로불능으로 연결되는 부상 질병(업무에 복귀 불가능), 장애가 남는 부상·질병
4 | 높음 | ■ 피해가 발생할 가능성이 높음 - 가드·방호덮개, 기타 안저장치를 설치하였으나, 해체되어 있으며 안전수칙·작업표준 등은 있지만 지키기 어렵고 많은 주의를 해야 함 | [8 empty] | 3 | 3개월 이상 (부상/질병) | 3개월 이상의 휴업을 수반하는 중대한 부상 또는 질병(일정시점에서는 업무에 복귀 가능)
3 | 보통 | ■ 부주의하면 피해가 발생할 가능성이 있음 - 가드·방호덮개 또는 안전장치 등은 설치되어 있지만, 작업불편 등으로 쉽게 해체하여 위험영역 접근, 위험원과 접촉이 있을 수 있으며, 안전수칙·작업표준 등은 있지만 준수하기 어려운 점이 있음 | [8 empty] | 2 | 3개월 미만 (부상/질병) | 3개월 미만의 휴업을 수반하는 부상 또는 질병
2 | 낮음 | ■ 피해가 발생할 가능성이 낮음 - 가드·방호덮개 등으로 보호되어 있고, 안저장치가 설치되어 있으며 위험영역 출입이 곤란한 상태이고 안전수칙·작업표준(서) 등이 정비되어 있고 준수하기 쉬우나 피해의 가능성이 남아 있음 | [8 empty] | 1 | 휴업불필요 | 치료(처치) 후 바로 원래의 작업을 수행할 수 있는 경미한 부상 또는 질병 (업무에 전혀 지장이 없음, 물질적 사고)
1 | 매우낮음 | ■ 피해가 발생할 가능성이 매우 낮음 - 가드·방호덮개 등으로 둘러싸여 있고 안전장치가 설치되어 있으며, 위험영역 출입이 곤란한 상태 등 전반적으로 안전조치가 잘 되어 있음
기계적 | 전기적 | 작업특성 | 작업환경 | 화학적 | 물리적 | 인간공학적 | 생물학적
1.1 협착위험 부분(감김, 끼임) | 2.1 감전(안전전압 초과) | 3.1 초음파·초저주파음 | 4.1 공간 및 이동통로 | 5.1 가스 | 6.1 기후/고온/저온(한랭) | 7.1 중량물 취급작업 | 8.1 병원성 미생물, 바이러스에 의한 감염
1.2 위험한 표면(절단, 베임, 긁힘) | 2.2 아크 | 3.2 근로자 실수(휴먼에러) | 4.2 주변 근로자 | 5.2 증기 | 6.2 조도(채광/조명) | 7.2 반복작업 | 8.2 유전자 변형물질(GMO)
1.3 기계·설비의 낙하, 비래, 전복, 붕괴, 전도위험 부분 | 2.3 정전기 | 3.3 질식위험·산소결핍 | 4.3 작업시간 | 5.3 에어로졸·흄 | 6.3 소음 | 7.3 불안정한 작업자세 | 8.3 알러지 및 미생물
1.4 충돌위험 부분 |  | 3.4 작업(조작) 도구 | 4.4 조직 안전문화 | 5.4 액체·미스트 | 6.4 진동 | 7.4 과도한 힘
1.5 넘어짐(미끄러짐, 걸림, 헛디딤) |  |  |  | 5.5 고체(분진/파우더) | 6.5 저압 또는 고압상태 | 7.5 접촉스트레스
1.6 추락위험 부분(개구부 등) |  |  |  | 5.6 반응성 물질 | 6.6 방사선
|  |  |  | 5.7 방사선 | 6.7 전자파
5.8 화재/폭발 위험
5.9 복사열/폭발과압